## Total Float ≤ 0
Activity ID | Activity Name | Activity Status | Cost Performance Index | Schedule Performance Index | Variance - BL Project Duration | Variance - BL Project Finish Date | Total Float | Schedule % Complete | Performance % Complete | Category | tooltip_text
P2080-074 | Activity P2080-074 | In Progress | 0 | 0 | -46 | 19 | 0 | 0 | 0.1818 | Total Float ≤ 0 | Activity ID: P2080-074<br>Activity Name: Activity P2080-074<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -46<br>Variance - BL Project Finish Date: 19<br>Total Float: 0.0
P2080-105 | Activity P2080-105 | In Progress | 0 | 0 | -34 | 5 | 0 | 0 | 0.4024 | Total Float ≤ 0 | Activity ID: P2080-105<br>Activity Name: Activity P2080-105<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -34<br>Variance - BL Project Finish Date: 5<br>Total Float: 0.0
P2080-246 | Activity P2080-246 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-246<br>Activity Name: Activity P2080-246<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-250 | Activity P2080-250 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-250<br>Activity Name: Activity P2080-250<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-309 | Activity P2080-309 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-309<br>Activity Name: Activity P2080-309<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-312 | Activity P2080-312 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-312<br>Activity Name: Activity P2080-312<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-318 | Activity P2080-318 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-318<br>Activity Name: Activity P2080-318<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-324 | Activity P2080-324 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-324<br>Activity Name: Activity P2080-324<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-347 | Activity P2080-347 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-347<br>Activity Name: Activity P2080-347<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-348 | Activity P2080-348 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-348<br>Activity Name: Activity P2080-348<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-387 | Activity P2080-387 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-387<br>Activity Name: Activity P2080-387<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-388 | Activity P2080-388 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-388<br>Activity Name: Activity P2080-388<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-403 | Activity P2080-403 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-403<br>Activity Name: Activity P2080-403<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-408 | Activity P2080-408 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-408<br>Activity Name: Activity P2080-408<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-419 | Activity P2080-419 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-419<br>Activity Name: Activity P2080-419<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-452 | Activity P2080-452 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-452<br>Activity Name: Activity P2080-452<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-465 | Activity P2080-465 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-465<br>Activity Name: Activity P2080-465<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-479 | Activity P2080-479 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-479<br>Activity Name: Activity P2080-479<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-485 | Activity P2080-485 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-485<br>Activity Name: Activity P2080-485<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-488 | Activity P2080-488 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-488<br>Activity Name: Activity P2080-488<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-507 | Activity P2080-507 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-507<br>Activity Name: Activity P2080-507<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-511 | Activity P2080-511 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-511<br>Activity Name: Activity P2080-511<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-544 | Activity P2080-544 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-544<br>Activity Name: Activity P2080-544<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-564 | Activity P2080-564 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-564<br>Activity Name: Activity P2080-564<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-584 | Activity P2080-584 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-584<br>Activity Name: Activity P2080-584<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-585 | Activity P2080-585 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-585<br>Activity Name: Activity P2080-585<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-614 | Activity P2080-614 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-614<br>Activity Name: Activity P2080-614<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-628 | Activity P2080-628 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-628<br>Activity Name: Activity P2080-628<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-647 | Activity P2080-647 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-647<br>Activity Name: Activity P2080-647<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-670 | Activity P2080-670 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-670<br>Activity Name: Activity P2080-670<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-686 | Activity P2080-686 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-686<br>Activity Name: Activity P2080-686<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-715 | Activity P2080-715 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-715<br>Activity Name: Activity P2080-715<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-718 | Activity P2080-718 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-718<br>Activity Name: Activity P2080-718<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-735 | Activity P2080-735 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-735<br>Activity Name: Activity P2080-735<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-736 | Activity P2080-736 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-736<br>Activity Name: Activity P2080-736<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-739 | Activity P2080-739 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-739<br>Activity Name: Activity P2080-739<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-749 | Activity P2080-749 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-749<br>Activity Name: Activity P2080-749<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-753 | Activity P2080-753 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-753<br>Activity Name: Activity P2080-753<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-758 | Activity P2080-758 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-758<br>Activity Name: Activity P2080-758<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-759 | Activity P2080-759 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-759<br>Activity Name: Activity P2080-759<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-766 | Activity P2080-766 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-766<br>Activity Name: Activity P2080-766<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-767 | Activity P2080-767 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-767<br>Activity Name: Activity P2080-767<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-768 | Activity P2080-768 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-768<br>Activity Name: Activity P2080-768<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-769 | Activity P2080-769 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-769<br>Activity Name: Activity P2080-769<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-778 | Activity P2080-778 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-778<br>Activity Name: Activity P2080-778<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-779 | Activity P2080-779 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-779<br>Activity Name: Activity P2080-779<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-786 | Activity P2080-786 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-786<br>Activity Name: Activity P2080-786<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-813 | Activity P2080-813 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-813<br>Activity Name: Activity P2080-813<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-817 | Activity P2080-817 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-817<br>Activity Name: Activity P2080-817<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-818 | Activity P2080-818 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-818<br>Activity Name: Activity P2080-818<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-819 | Activity P2080-819 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-819<br>Activity Name: Activity P2080-819<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-822 | Activity P2080-822 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-822<br>Activity Name: Activity P2080-822<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-836 | Activity P2080-836 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-836<br>Activity Name: Activity P2080-836<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-846 | Activity P2080-846 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-846<br>Activity Name: Activity P2080-846<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-867 | Activity P2080-867 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-867<br>Activity Name: Activity P2080-867<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-872 | Activity P2080-872 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-872<br>Activity Name: Activity P2080-872<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-879 | Activity P2080-879 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-879<br>Activity Name: Activity P2080-879<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-880 | Activity P2080-880 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-880<br>Activity Name: Activity P2080-880<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-881 | Activity P2080-881 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-881<br>Activity Name: Activity P2080-881<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-882 | Activity P2080-882 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-882<br>Activity Name: Activity P2080-882<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-885 | Activity P2080-885 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-885<br>Activity Name: Activity P2080-885<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-887 | Activity P2080-887 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-887<br>Activity Name: Activity P2080-887<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-889 | Activity P2080-889 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-889<br>Activity Name: Activity P2080-889<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-899 | Activity P2080-899 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-899<br>Activity Name: Activity P2080-899<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-900 | Activity P2080-900 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-900<br>Activity Name: Activity P2080-900<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-902 | Activity P2080-902 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-902<br>Activity Name: Activity P2080-902<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-903 | Activity P2080-903 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-903<br>Activity Name: Activity P2080-903<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-910 | Activity P2080-910 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-910<br>Activity Name: Activity P2080-910<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-912 | Activity P2080-912 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-912<br>Activity Name: Activity P2080-912<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-913 | Activity P2080-913 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-913<br>Activity Name: Activity P2080-913<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-915 | Activity P2080-915 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-915<br>Activity Name: Activity P2080-915<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-916 | Activity P2080-916 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-916<br>Activity Name: Activity P2080-916<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-917 | Activity P2080-917 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-917<br>Activity Name: Activity P2080-917<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-918 | Activity P2080-918 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-918<br>Activity Name: Activity P2080-918<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-919 | Activity P2080-919 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-919<br>Activity Name: Activity P2080-919<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-920 | Activity P2080-920 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-920<br>Activity Name: Activity P2080-920<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0
P2080-921 | Activity P2080-921 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Float ≤ 0 | Activity ID: P2080-921<br>Activity Name: Activity P2080-921<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 0.0

## 0 < Total Float ≤ 10
Activity ID | Activity Name | Activity Status | Cost Performance Index | Schedule Performance Index | Variance - BL Project Duration | Variance - BL Project Finish Date | Total Float | Schedule % Complete | Performance % Complete | Category | tooltip_text
P2080-078 | Activity P2080-078 | In Progress | 0 | 0 | -10 | 65 | 5 | 0 | 0.3407 | 0 < Total Float ≤ 10 | Activity ID: P2080-078<br>Activity Name: Activity P2080-078<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -10<br>Variance - BL Project Finish Date: 65<br>Total Float: 5.0
P2080-137 | Activity P2080-137 | In Progress | 0 | 0.87 | -9 | -18 | 1 | 1 | 0.8654 | 0 < Total Float ≤ 10 | Activity ID: P2080-137<br>Activity Name: Activity P2080-137<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -9<br>Variance - BL Project Finish Date: -18<br>Total Float: 1.0
P2080-181 | Activity P2080-181 | In Progress | 0 | 0 | 0 | 21 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-181<br>Activity Name: Activity P2080-181<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 21<br>Total Float: 1.0
P2080-195 | Activity P2080-195 | In Progress | 0 | 0.67 | 4 | -4 | 2 | 1 | 0.6667 | 0 < Total Float ≤ 10 | Activity ID: P2080-195<br>Activity Name: Activity P2080-195<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 4<br>Variance - BL Project Finish Date: -4<br>Total Float: 2.0
P2080-197 | Activity P2080-197 | In Progress | 0 | 0 | -18 | 0 | 6 | 0 | 0.5964 | 0 < Total Float ≤ 10 | Activity ID: P2080-197<br>Activity Name: Activity P2080-197<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -18<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-204 | Activity P2080-204 | Not Started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-204<br>Activity Name: Activity P2080-204<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 1.0
P2080-205 | Activity P2080-205 | Not Started | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-205<br>Activity Name: Activity P2080-205<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 5.0
P2080-206 | Activity P2080-206 | Not Started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-206<br>Activity Name: Activity P2080-206<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 1.0
P2080-207 | Activity P2080-207 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-207<br>Activity Name: Activity P2080-207<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-210 | Activity P2080-210 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-210<br>Activity Name: Activity P2080-210<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-239 | Activity P2080-239 | Not Started | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-239<br>Activity Name: Activity P2080-239<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 2.0
P2080-242 | Activity P2080-242 | Not Started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-242<br>Activity Name: Activity P2080-242<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 1.0
P2080-245 | Activity P2080-245 | Not Started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-245<br>Activity Name: Activity P2080-245<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 1.0
P2080-256 | Activity P2080-256 | Not Started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-256<br>Activity Name: Activity P2080-256<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 1.0
P2080-286 | Activity P2080-286 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-286<br>Activity Name: Activity P2080-286<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-319 | Activity P2080-319 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-319<br>Activity Name: Activity P2080-319<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-320 | Activity P2080-320 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-320<br>Activity Name: Activity P2080-320<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-321 | Activity P2080-321 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-321<br>Activity Name: Activity P2080-321<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-322 | Activity P2080-322 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-322<br>Activity Name: Activity P2080-322<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-328 | Activity P2080-328 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-328<br>Activity Name: Activity P2080-328<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-362 | Activity P2080-362 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-362<br>Activity Name: Activity P2080-362<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-363 | Activity P2080-363 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-363<br>Activity Name: Activity P2080-363<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-407 | Activity P2080-407 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-407<br>Activity Name: Activity P2080-407<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-448 | Activity P2080-448 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-448<br>Activity Name: Activity P2080-448<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-453 | Activity P2080-453 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-453<br>Activity Name: Activity P2080-453<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-478 | Activity P2080-478 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-478<br>Activity Name: Activity P2080-478<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-481 | Activity P2080-481 | Not Started | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-481<br>Activity Name: Activity P2080-481<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 5.0
P2080-497 | Activity P2080-497 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-497<br>Activity Name: Activity P2080-497<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-545 | Activity P2080-545 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-545<br>Activity Name: Activity P2080-545<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-548 | Activity P2080-548 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-548<br>Activity Name: Activity P2080-548<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-555 | Activity P2080-555 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-555<br>Activity Name: Activity P2080-555<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-556 | Activity P2080-556 | Not Started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-556<br>Activity Name: Activity P2080-556<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 1.0
P2080-565 | Activity P2080-565 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-565<br>Activity Name: Activity P2080-565<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-566 | Activity P2080-566 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-566<br>Activity Name: Activity P2080-566<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-567 | Activity P2080-567 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-567<br>Activity Name: Activity P2080-567<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-569 | Activity P2080-569 | Not Started | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-569<br>Activity Name: Activity P2080-569<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 10.0
P2080-589 | Activity P2080-589 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-589<br>Activity Name: Activity P2080-589<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-594 | Activity P2080-594 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-594<br>Activity Name: Activity P2080-594<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-595 | Activity P2080-595 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-595<br>Activity Name: Activity P2080-595<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-609 | Activity P2080-609 | Not Started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-609<br>Activity Name: Activity P2080-609<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 1.0
P2080-630 | Activity P2080-630 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-630<br>Activity Name: Activity P2080-630<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-637 | Activity P2080-637 | Not Started | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-637<br>Activity Name: Activity P2080-637<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 5.0
P2080-648 | Activity P2080-648 | Not Started | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-648<br>Activity Name: Activity P2080-648<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 5.0
P2080-654 | Activity P2080-654 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-654<br>Activity Name: Activity P2080-654<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-664 | Activity P2080-664 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-664<br>Activity Name: Activity P2080-664<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-671 | Activity P2080-671 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-671<br>Activity Name: Activity P2080-671<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-672 | Activity P2080-672 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-672<br>Activity Name: Activity P2080-672<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-673 | Activity P2080-673 | Not Started | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-673<br>Activity Name: Activity P2080-673<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 5.0
P2080-679 | Activity P2080-679 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-679<br>Activity Name: Activity P2080-679<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-682 | Activity P2080-682 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-682<br>Activity Name: Activity P2080-682<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-696 | Activity P2080-696 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-696<br>Activity Name: Activity P2080-696<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-697 | Activity P2080-697 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-697<br>Activity Name: Activity P2080-697<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-702 | Activity P2080-702 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-702<br>Activity Name: Activity P2080-702<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-707 | Activity P2080-707 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-707<br>Activity Name: Activity P2080-707<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-709 | Activity P2080-709 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-709<br>Activity Name: Activity P2080-709<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-711 | Activity P2080-711 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-711<br>Activity Name: Activity P2080-711<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-712 | Activity P2080-712 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-712<br>Activity Name: Activity P2080-712<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-716 | Activity P2080-716 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-716<br>Activity Name: Activity P2080-716<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-725 | Activity P2080-725 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-725<br>Activity Name: Activity P2080-725<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-726 | Activity P2080-726 | Not Started | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-726<br>Activity Name: Activity P2080-726<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 10.0
P2080-729 | Activity P2080-729 | Not Started | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-729<br>Activity Name: Activity P2080-729<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 10.0
P2080-740 | Activity P2080-740 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-740<br>Activity Name: Activity P2080-740<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-761 | Activity P2080-761 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-761<br>Activity Name: Activity P2080-761<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-776 | Activity P2080-776 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-776<br>Activity Name: Activity P2080-776<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-785 | Activity P2080-785 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-785<br>Activity Name: Activity P2080-785<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-798 | Activity P2080-798 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-798<br>Activity Name: Activity P2080-798<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-799 | Activity P2080-799 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-799<br>Activity Name: Activity P2080-799<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-800 | Activity P2080-800 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-800<br>Activity Name: Activity P2080-800<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-814 | Activity P2080-814 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-814<br>Activity Name: Activity P2080-814<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-820 | Activity P2080-820 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-820<br>Activity Name: Activity P2080-820<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-825 | Activity P2080-825 | Not Started | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-825<br>Activity Name: Activity P2080-825<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 6.0
P2080-826 | Activity P2080-826 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-826<br>Activity Name: Activity P2080-826<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-827 | Activity P2080-827 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-827<br>Activity Name: Activity P2080-827<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-828 | Activity P2080-828 | Not Started | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-828<br>Activity Name: Activity P2080-828<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 10.0
P2080-830 | Activity P2080-830 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-830<br>Activity Name: Activity P2080-830<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-835 | Activity P2080-835 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-835<br>Activity Name: Activity P2080-835<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-837 | Activity P2080-837 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-837<br>Activity Name: Activity P2080-837<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-838 | Activity P2080-838 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-838<br>Activity Name: Activity P2080-838<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-839 | Activity P2080-839 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-839<br>Activity Name: Activity P2080-839<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-840 | Activity P2080-840 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-840<br>Activity Name: Activity P2080-840<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-841 | Activity P2080-841 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-841<br>Activity Name: Activity P2080-841<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-842 | Activity P2080-842 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-842<br>Activity Name: Activity P2080-842<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-843 | Activity P2080-843 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-843<br>Activity Name: Activity P2080-843<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-845 | Activity P2080-845 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-845<br>Activity Name: Activity P2080-845<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-847 | Activity P2080-847 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-847<br>Activity Name: Activity P2080-847<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-848 | Activity P2080-848 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-848<br>Activity Name: Activity P2080-848<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-849 | Activity P2080-849 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-849<br>Activity Name: Activity P2080-849<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-850 | Activity P2080-850 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-850<br>Activity Name: Activity P2080-850<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-851 | Activity P2080-851 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-851<br>Activity Name: Activity P2080-851<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-852 | Activity P2080-852 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-852<br>Activity Name: Activity P2080-852<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-853 | Activity P2080-853 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-853<br>Activity Name: Activity P2080-853<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-854 | Activity P2080-854 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-854<br>Activity Name: Activity P2080-854<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-855 | Activity P2080-855 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-855<br>Activity Name: Activity P2080-855<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-856 | Activity P2080-856 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-856<br>Activity Name: Activity P2080-856<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-857 | Activity P2080-857 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-857<br>Activity Name: Activity P2080-857<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-858 | Activity P2080-858 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-858<br>Activity Name: Activity P2080-858<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-859 | Activity P2080-859 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-859<br>Activity Name: Activity P2080-859<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-862 | Activity P2080-862 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-862<br>Activity Name: Activity P2080-862<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-863 | Activity P2080-863 | Not Started | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-863<br>Activity Name: Activity P2080-863<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 7.0
P2080-873 | Activity P2080-873 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-873<br>Activity Name: Activity P2080-873<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-874 | Activity P2080-874 | Not Started | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-874<br>Activity Name: Activity P2080-874<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 9.0
P2080-875 | Activity P2080-875 | Not Started | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-875<br>Activity Name: Activity P2080-875<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 8.0
P2080-883 | Activity P2080-883 | Not Started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-883<br>Activity Name: Activity P2080-883<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 1.0
P2080-907 | Activity P2080-907 | Not Started | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 < Total Float ≤ 10 | Activity ID: P2080-907<br>Activity Name: Activity P2080-907<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 2.0

## 10 < Total Float ≤ 20
Activity ID | Activity Name | Activity Status | Cost Performance Index | Schedule Performance Index | Variance - BL Project Duration | Variance - BL Project Finish Date | Total Float | Schedule % Complete | Performance % Complete | Category | tooltip_text
P2080-133 | Activity P2080-133 | In Progress | 0 | 0.48 | -16 | -16 | 13 | 1 | 0.4794 | 10 < Total Float ≤ 20 | Activity ID: P2080-133<br>Activity Name: Activity P2080-133<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -16<br>Variance - BL Project Finish Date: -16<br>Total Float: 13.0
P2080-176 | Activity P2080-176 | In Progress | 0 | 0.8 | -5 | -5 | 11 | 1 | 0.7982 | 10 < Total Float ≤ 20 | Activity ID: P2080-176<br>Activity Name: Activity P2080-176<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -5<br>Variance - BL Project Finish Date: -5<br>Total Float: 11.0
P2080-182 | Activity P2080-182 | In Progress | 0 | 0 | 8 | -49 | 17 | 1 | 1 | 10 < Total Float ≤ 20 | Activity ID: P2080-182<br>Activity Name: Activity P2080-182<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 8<br>Variance - BL Project Finish Date: -49<br>Total Float: 17.0
P2080-185 | Activity P2080-185 | In Progress | 0 | 0 | 5 | 27 | 14 | 0 | 0.7 | 10 < Total Float ≤ 20 | Activity ID: P2080-185<br>Activity Name: Activity P2080-185<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 5<br>Variance - BL Project Finish Date: 27<br>Total Float: 14.0
P2080-190 | Activity P2080-190 | In Progress | 0 | 0.25 | 0 | -21 | 12 | 0.52 | 0.1291 | 10 < Total Float ≤ 20 | Activity ID: P2080-190<br>Activity Name: Activity P2080-190<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: -21<br>Total Float: 12.0
P2080-196 | Activity P2080-196 | In Progress | 0 | 0.65 | -14 | -30 | 13 | 1 | 0.6486 | 10 < Total Float ≤ 20 | Activity ID: P2080-196<br>Activity Name: Activity P2080-196<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -14<br>Variance - BL Project Finish Date: -30<br>Total Float: 13.0
P2080-208 | Activity P2080-208 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-208<br>Activity Name: Activity P2080-208<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-209 | Activity P2080-209 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-209<br>Activity Name: Activity P2080-209<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-211 | Activity P2080-211 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-211<br>Activity Name: Activity P2080-211<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-212 | Activity P2080-212 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-212<br>Activity Name: Activity P2080-212<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-249 | Activity P2080-249 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-249<br>Activity Name: Activity P2080-249<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-251 | Activity P2080-251 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-251<br>Activity Name: Activity P2080-251<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-260 | Activity P2080-260 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-260<br>Activity Name: Activity P2080-260<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-262 | Activity P2080-262 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-262<br>Activity Name: Activity P2080-262<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-263 | Activity P2080-263 | Not Started | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-263<br>Activity Name: Activity P2080-263<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 15.0
P2080-273 | Activity P2080-273 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-273<br>Activity Name: Activity P2080-273<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-285 | Activity P2080-285 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-285<br>Activity Name: Activity P2080-285<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-295 | Activity P2080-295 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-295<br>Activity Name: Activity P2080-295<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-296 | Activity P2080-296 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-296<br>Activity Name: Activity P2080-296<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-313 | Activity P2080-313 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-313<br>Activity Name: Activity P2080-313<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-315 | Activity P2080-315 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-315<br>Activity Name: Activity P2080-315<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-337 | Activity P2080-337 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-337<br>Activity Name: Activity P2080-337<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-342 | Activity P2080-342 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-342<br>Activity Name: Activity P2080-342<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-349 | Activity P2080-349 | Not Started | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-349<br>Activity Name: Activity P2080-349<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 16.0
P2080-352 | Activity P2080-352 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-352<br>Activity Name: Activity P2080-352<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-389 | Activity P2080-389 | Not Started | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-389<br>Activity Name: Activity P2080-389<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 16.0
P2080-390 | Activity P2080-390 | Not Started | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-390<br>Activity Name: Activity P2080-390<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 16.0
P2080-393 | Activity P2080-393 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-393<br>Activity Name: Activity P2080-393<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-398 | Activity P2080-398 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-398<br>Activity Name: Activity P2080-398<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-409 | Activity P2080-409 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-409<br>Activity Name: Activity P2080-409<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-422 | Activity P2080-422 | Not Started | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-422<br>Activity Name: Activity P2080-422<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 16.0
P2080-431 | Activity P2080-431 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-431<br>Activity Name: Activity P2080-431<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-433 | Activity P2080-433 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-433<br>Activity Name: Activity P2080-433<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-439 | Activity P2080-439 | Not Started | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-439<br>Activity Name: Activity P2080-439<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 16.0
P2080-443 | Activity P2080-443 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-443<br>Activity Name: Activity P2080-443<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-498 | Activity P2080-498 | Not Started | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-498<br>Activity Name: Activity P2080-498<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 16.0
P2080-505 | Activity P2080-505 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-505<br>Activity Name: Activity P2080-505<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-512 | Activity P2080-512 | Not Started | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-512<br>Activity Name: Activity P2080-512<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 16.0
P2080-519 | Activity P2080-519 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-519<br>Activity Name: Activity P2080-519<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-520 | Activity P2080-520 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-520<br>Activity Name: Activity P2080-520<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-521 | Activity P2080-521 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-521<br>Activity Name: Activity P2080-521<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-524 | Activity P2080-524 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-524<br>Activity Name: Activity P2080-524<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-536 | Activity P2080-536 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-536<br>Activity Name: Activity P2080-536<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-538 | Activity P2080-538 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-538<br>Activity Name: Activity P2080-538<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-558 | Activity P2080-558 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-558<br>Activity Name: Activity P2080-558<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-563 | Activity P2080-563 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-563<br>Activity Name: Activity P2080-563<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-568 | Activity P2080-568 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-568<br>Activity Name: Activity P2080-568<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-570 | Activity P2080-570 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-570<br>Activity Name: Activity P2080-570<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-615 | Activity P2080-615 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-615<br>Activity Name: Activity P2080-615<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-616 | Activity P2080-616 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-616<br>Activity Name: Activity P2080-616<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-624 | Activity P2080-624 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-624<br>Activity Name: Activity P2080-624<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-625 | Activity P2080-625 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-625<br>Activity Name: Activity P2080-625<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-626 | Activity P2080-626 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-626<br>Activity Name: Activity P2080-626<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-629 | Activity P2080-629 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-629<br>Activity Name: Activity P2080-629<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-634 | Activity P2080-634 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-634<br>Activity Name: Activity P2080-634<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-638 | Activity P2080-638 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-638<br>Activity Name: Activity P2080-638<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-639 | Activity P2080-639 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-639<br>Activity Name: Activity P2080-639<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-643 | Activity P2080-643 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-643<br>Activity Name: Activity P2080-643<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-651 | Activity P2080-651 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-651<br>Activity Name: Activity P2080-651<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-655 | Activity P2080-655 | Not Started | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-655<br>Activity Name: Activity P2080-655<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 18.0
P2080-665 | Activity P2080-665 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-665<br>Activity Name: Activity P2080-665<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-669 | Activity P2080-669 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-669<br>Activity Name: Activity P2080-669<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-674 | Activity P2080-674 | Not Started | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-674<br>Activity Name: Activity P2080-674<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 18.0
P2080-680 | Activity P2080-680 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-680<br>Activity Name: Activity P2080-680<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-683 | Activity P2080-683 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-683<br>Activity Name: Activity P2080-683<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-685 | Activity P2080-685 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-685<br>Activity Name: Activity P2080-685<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-687 | Activity P2080-687 | Not Started | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-687<br>Activity Name: Activity P2080-687<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 18.0
P2080-710 | Activity P2080-710 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-710<br>Activity Name: Activity P2080-710<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-719 | Activity P2080-719 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-719<br>Activity Name: Activity P2080-719<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-720 | Activity P2080-720 | Not Started | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-720<br>Activity Name: Activity P2080-720<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 18.0
P2080-737 | Activity P2080-737 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-737<br>Activity Name: Activity P2080-737<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-754 | Activity P2080-754 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-754<br>Activity Name: Activity P2080-754<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-756 | Activity P2080-756 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-756<br>Activity Name: Activity P2080-756<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-760 | Activity P2080-760 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-760<br>Activity Name: Activity P2080-760<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-763 | Activity P2080-763 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-763<br>Activity Name: Activity P2080-763<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-770 | Activity P2080-770 | Not Started | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-770<br>Activity Name: Activity P2080-770<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 12.0
P2080-771 | Activity P2080-771 | Not Started | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-771<br>Activity Name: Activity P2080-771<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 18.0
P2080-772 | Activity P2080-772 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-772<br>Activity Name: Activity P2080-772<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-781 | Activity P2080-781 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-781<br>Activity Name: Activity P2080-781<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-787 | Activity P2080-787 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-787<br>Activity Name: Activity P2080-787<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-793 | Activity P2080-793 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-793<br>Activity Name: Activity P2080-793<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-794 | Activity P2080-794 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-794<br>Activity Name: Activity P2080-794<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-802 | Activity P2080-802 | Not Started | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-802<br>Activity Name: Activity P2080-802<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 17.0
P2080-805 | Activity P2080-805 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-805<br>Activity Name: Activity P2080-805<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-806 | Activity P2080-806 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-806<br>Activity Name: Activity P2080-806<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-807 | Activity P2080-807 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-807<br>Activity Name: Activity P2080-807<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-808 | Activity P2080-808 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-808<br>Activity Name: Activity P2080-808<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-810 | Activity P2080-810 | Not Started | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-810<br>Activity Name: Activity P2080-810<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 19.0
P2080-811 | Activity P2080-811 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-811<br>Activity Name: Activity P2080-811<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-812 | Activity P2080-812 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-812<br>Activity Name: Activity P2080-812<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-815 | Activity P2080-815 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-815<br>Activity Name: Activity P2080-815<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-816 | Activity P2080-816 | Not Started | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-816<br>Activity Name: Activity P2080-816<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 20.0
P2080-821 | Activity P2080-821 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-821<br>Activity Name: Activity P2080-821<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-829 | Activity P2080-829 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-829<br>Activity Name: Activity P2080-829<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-860 | Activity P2080-860 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-860<br>Activity Name: Activity P2080-860<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-861 | Activity P2080-861 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-861<br>Activity Name: Activity P2080-861<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-864 | Activity P2080-864 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-864<br>Activity Name: Activity P2080-864<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-865 | Activity P2080-865 | Not Started | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-865<br>Activity Name: Activity P2080-865<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 15.0
P2080-866 | Activity P2080-866 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-866<br>Activity Name: Activity P2080-866<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-868 | Activity P2080-868 | Not Started | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-868<br>Activity Name: Activity P2080-868<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 13.0
P2080-869 | Activity P2080-869 | Not Started | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-869<br>Activity Name: Activity P2080-869<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 14.0
P2080-870 | Activity P2080-870 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-870<br>Activity Name: Activity P2080-870<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-871 | Activity P2080-871 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-871<br>Activity Name: Activity P2080-871<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-876 | Activity P2080-876 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-876<br>Activity Name: Activity P2080-876<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0
P2080-908 | Activity P2080-908 | Not Started | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 10 < Total Float ≤ 20 | Activity ID: P2080-908<br>Activity Name: Activity P2080-908<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 11.0

## Total Float > 20
Activity ID | Activity Name | Activity Status | Cost Performance Index | Schedule Performance Index | Variance - BL Project Duration | Variance - BL Project Finish Date | Total Float | Schedule % Complete | Performance % Complete | Category | tooltip_text
P2080-036 | Activity P2080-036 | In Progress | 0 | 0.67 | -54 | -54 | 84 | 1 | 0.6742 | Total Float > 20 | Activity ID: P2080-036<br>Activity Name: Activity P2080-036<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -54<br>Variance - BL Project Finish Date: -54<br>Total Float: 84.0
P2080-037 | Activity P2080-037 | In Progress | 0 | 0 | 0 | 0 | 298 | 0.7629 | 0 | Total Float > 20 | Activity ID: P2080-037<br>Activity Name: Activity P2080-037<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 298.0
P2080-038 | Activity P2080-038 | In Progress | 0 | 0 | -74 | -74 | 239 | 0.9024 | 0 | Total Float > 20 | Activity ID: P2080-038<br>Activity Name: Activity P2080-038<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -74<br>Variance - BL Project Finish Date: -74<br>Total Float: 239.0
P2080-039 | Activity P2080-039 | In Progress | 0 | 0 | 0 | 0 | 229 | 0.4458 | 0 | Total Float > 20 | Activity ID: P2080-039<br>Activity Name: Activity P2080-039<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 229.0
P2080-040 | Activity P2080-040 | In Progress | 0 | 0 | 0 | 0 | 180 | 0.3442 | 0 | Total Float > 20 | Activity ID: P2080-040<br>Activity Name: Activity P2080-040<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 180.0
P2080-041 | Activity P2080-041 | In Progress | 0 | 0 | 0 | 0 | 120 | 0.2691 | 0 | Total Float > 20 | Activity ID: P2080-041<br>Activity Name: Activity P2080-041<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 120.0
P2080-042 | Activity P2080-042 | In Progress | 0 | 0 | 0 | 0 | 108 | 0.2578 | 0 | Total Float > 20 | Activity ID: P2080-042<br>Activity Name: Activity P2080-042<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 108.0
P2080-043 | Activity P2080-043 | In Progress | 0 | 0 | 0 | 0 | 22 | 0.1984 | 0 | Total Float > 20 | Activity ID: P2080-043<br>Activity Name: Activity P2080-043<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-044 | Activity P2080-044 | In Progress | 0 | 0 | 0 | 0 | 697 | 0.6607 | 0 | Total Float > 20 | Activity ID: P2080-044<br>Activity Name: Activity P2080-044<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 697.0
P2080-045 | Activity P2080-045 | In Progress | 0 | 0 | 0 | 0 | 654 | 0.4774 | 0 | Total Float > 20 | Activity ID: P2080-045<br>Activity Name: Activity P2080-045<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 654.0
P2080-046 | Activity P2080-046 | In Progress | 0 | 0 | 0 | 0 | 654 | 0.4774 | 0 | Total Float > 20 | Activity ID: P2080-046<br>Activity Name: Activity P2080-046<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 654.0
P2080-047 | Activity P2080-047 | In Progress | 0 | 0 | 0 | 0 | 545 | 0.2803 | 0 | Total Float > 20 | Activity ID: P2080-047<br>Activity Name: Activity P2080-047<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 545.0
P2080-048 | Activity P2080-048 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-048<br>Activity Name: Activity P2080-048<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-049 | Activity P2080-049 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-049<br>Activity Name: Activity P2080-049<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-050 | Activity P2080-050 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-050<br>Activity Name: Activity P2080-050<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-051 | Activity P2080-051 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-051<br>Activity Name: Activity P2080-051<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-052 | Activity P2080-052 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-052<br>Activity Name: Activity P2080-052<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-053 | Activity P2080-053 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-053<br>Activity Name: Activity P2080-053<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-054 | Activity P2080-054 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-054<br>Activity Name: Activity P2080-054<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-055 | Activity P2080-055 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-055<br>Activity Name: Activity P2080-055<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-056 | Activity P2080-056 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-056<br>Activity Name: Activity P2080-056<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-057 | Activity P2080-057 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-057<br>Activity Name: Activity P2080-057<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-058 | Activity P2080-058 | In Progress | 0 | 0 | 0 | 0 | 500 | 0.2395 | 0 | Total Float > 20 | Activity ID: P2080-058<br>Activity Name: Activity P2080-058<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 500.0
P2080-059 | Activity P2080-059 | In Progress | 0 | 0 | 0 | 0 | 480 | 0.2249 | 0 | Total Float > 20 | Activity ID: P2080-059<br>Activity Name: Activity P2080-059<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 480.0
P2080-060 | Activity P2080-060 | In Progress | 0 | 0 | 0 | 0 | 480 | 0.2249 | 0 | Total Float > 20 | Activity ID: P2080-060<br>Activity Name: Activity P2080-060<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 480.0
P2080-061 | Activity P2080-061 | In Progress | 0 | 0 | 0 | 0 | 458 | 0.2108 | 0 | Total Float > 20 | Activity ID: P2080-061<br>Activity Name: Activity P2080-061<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 458.0
P2080-062 | Activity P2080-062 | In Progress | 0 | 0 | 0 | 0 | 393 | 0.1779 | 0 | Total Float > 20 | Activity ID: P2080-062<br>Activity Name: Activity P2080-062<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 393.0
P2080-063 | Activity P2080-063 | In Progress | 0 | 0 | 0 | 0 | 393 | 0.1779 | 0 | Total Float > 20 | Activity ID: P2080-063<br>Activity Name: Activity P2080-063<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 393.0
P2080-120 | Activity P2080-120 | In Progress | 0 | 0 | -21 | 15 | 30 | 0 | 0.508 | Total Float > 20 | Activity ID: P2080-120<br>Activity Name: Activity P2080-120<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -21<br>Variance - BL Project Finish Date: 15<br>Total Float: 30.0
P2080-125 | Activity P2080-125 | In Progress | 0 | 0.61 | -26 | -27 | 32 | 1 | 0.6139 | Total Float > 20 | Activity ID: P2080-125<br>Activity Name: Activity P2080-125<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -26<br>Variance - BL Project Finish Date: -27<br>Total Float: 32.0
P2080-128 | Activity P2080-128 | In Progress | 0 | 0 | -18 | 6 | 41 | 0 | 0.4878 | Total Float > 20 | Activity ID: P2080-128<br>Activity Name: Activity P2080-128<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -18<br>Variance - BL Project Finish Date: 6<br>Total Float: 41.0
P2080-134 | Activity P2080-134 | In Progress | 0 | 0.61 | -21 | -21 | 100 | 1 | 0.6139 | Total Float > 20 | Activity ID: P2080-134<br>Activity Name: Activity P2080-134<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -21<br>Variance - BL Project Finish Date: -21<br>Total Float: 100.0
P2080-138 | Activity P2080-138 | In Progress | 0 | 0 | 10 | 36 | 28 | 0 | 0.6499 | Total Float > 20 | Activity ID: P2080-138<br>Activity Name: Activity P2080-138<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 10<br>Variance - BL Project Finish Date: 36<br>Total Float: 28.0
P2080-156 | Activity P2080-156 | In Progress | 0 | 0 | -11 | 5 | 24 | 0 | 0.5078 | Total Float > 20 | Activity ID: P2080-156<br>Activity Name: Activity P2080-156<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -11<br>Variance - BL Project Finish Date: 5<br>Total Float: 24.0
P2080-157 | Activity P2080-157 | In Progress | 0 | 0 | -11 | 5 | 24 | 0 | 0.5078 | Total Float > 20 | Activity ID: P2080-157<br>Activity Name: Activity P2080-157<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -11<br>Variance - BL Project Finish Date: 5<br>Total Float: 24.0
P2080-161 | Activity P2080-161 | In Progress | 0 | 0 | -25 | 0 | 25 | 0 | 0.4733 | Total Float > 20 | Activity ID: P2080-161<br>Activity Name: Activity P2080-161<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -25<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-177 | Activity P2080-177 | In Progress | 0 | 0 | -14 | 1 | 55 | 0 | 0.7982 | Total Float > 20 | Activity ID: P2080-177<br>Activity Name: Activity P2080-177<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -14<br>Variance - BL Project Finish Date: 1<br>Total Float: 55.0
P2080-188 | Activity P2080-188 | In Progress | 0 | 0 | 0 | -79 | 449 | 1 | 0 | Total Float > 20 | Activity ID: P2080-188<br>Activity Name: Activity P2080-188<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: -79<br>Total Float: 449.0
P2080-198 | Activity P2080-198 | In Progress | 0 | 0.6 | -19 | -35 | 107 | 1 | 0.5964 | Total Float > 20 | Activity ID: P2080-198<br>Activity Name: Activity P2080-198<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -19<br>Variance - BL Project Finish Date: -35<br>Total Float: 107.0
P2080-201 | Activity P2080-201 | In Progress | 0 | 0 | 0 | -16 | 26 | 1 | 0 | Total Float > 20 | Activity ID: P2080-201<br>Activity Name: Activity P2080-201<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: -16<br>Total Float: 26.0
P2080-202 | Activity P2080-202 | In Progress | 0 | 0.65 | -8 | -23 | 23 | 1 | 0.6497 | Total Float > 20 | Activity ID: P2080-202<br>Activity Name: Activity P2080-202<br>Activity Status: In Progress<br><br>Variance - BL Project Duration: -8<br>Variance - BL Project Finish Date: -23<br>Total Float: 23.0
P2080-203 | Activity P2080-203 | Not Started | 0 | 0 | 0 | 0 | 142 | 0 | 0 | Total Float > 20 | Activity ID: P2080-203<br>Activity Name: Activity P2080-203<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 142.0
P2080-213 | Activity P2080-213 | Not Started | 0 | 0 | 0 | 0 | 47 | 0 | 0 | Total Float > 20 | Activity ID: P2080-213<br>Activity Name: Activity P2080-213<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 47.0
P2080-214 | Activity P2080-214 | Not Started | 0 | 0 | 0 | 0 | 53 | 0 | 0 | Total Float > 20 | Activity ID: P2080-214<br>Activity Name: Activity P2080-214<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 53.0
P2080-215 | Activity P2080-215 | Not Started | 0 | 0 | 0 | 0 | 64 | 0 | 0 | Total Float > 20 | Activity ID: P2080-215<br>Activity Name: Activity P2080-215<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 64.0
P2080-216 | Activity P2080-216 | Not Started | 0 | 0 | 0 | 0 | 64 | 0 | 0 | Total Float > 20 | Activity ID: P2080-216<br>Activity Name: Activity P2080-216<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 64.0
P2080-217 | Activity P2080-217 | Not Started | 0 | 0 | 0 | 0 | 64 | 0 | 0 | Total Float > 20 | Activity ID: P2080-217<br>Activity Name: Activity P2080-217<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 64.0
P2080-218 | Activity P2080-218 | Not Started | 0 | 0 | 0 | 0 | 64 | 0 | 0 | Total Float > 20 | Activity ID: P2080-218<br>Activity Name: Activity P2080-218<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 64.0
P2080-219 | Activity P2080-219 | Not Started | 0 | 0 | 0 | 0 | 104 | 0 | 0 | Total Float > 20 | Activity ID: P2080-219<br>Activity Name: Activity P2080-219<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 104.0
P2080-220 | Activity P2080-220 | Not Started | 0 | 0 | 0 | 0 | 104 | 0 | 0 | Total Float > 20 | Activity ID: P2080-220<br>Activity Name: Activity P2080-220<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 104.0
P2080-221 | Activity P2080-221 | Not Started | 0 | 0 | 0 | 0 | 104 | 0 | 0 | Total Float > 20 | Activity ID: P2080-221<br>Activity Name: Activity P2080-221<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 104.0
P2080-222 | Activity P2080-222 | Not Started | 0 | 0 | 0 | 0 | 104 | 0 | 0 | Total Float > 20 | Activity ID: P2080-222<br>Activity Name: Activity P2080-222<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 104.0
P2080-223 | Activity P2080-223 | Not Started | 0 | 0 | 0 | 0 | 157 | 0 | 0 | Total Float > 20 | Activity ID: P2080-223<br>Activity Name: Activity P2080-223<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 157.0
P2080-224 | Activity P2080-224 | Not Started | 0 | 0 | 0 | 0 | 165 | 0 | 0 | Total Float > 20 | Activity ID: P2080-224<br>Activity Name: Activity P2080-224<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 165.0
P2080-225 | Activity P2080-225 | Not Started | 0 | 0 | 0 | 0 | 173 | 0 | 0 | Total Float > 20 | Activity ID: P2080-225<br>Activity Name: Activity P2080-225<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 173.0
P2080-226 | Activity P2080-226 | Not Started | 0 | 0 | 0 | 0 | 157 | 0 | 0 | Total Float > 20 | Activity ID: P2080-226<br>Activity Name: Activity P2080-226<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 157.0
P2080-227 | Activity P2080-227 | Not Started | 0 | 0 | 0 | 0 | 165 | 0 | 0 | Total Float > 20 | Activity ID: P2080-227<br>Activity Name: Activity P2080-227<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 165.0
P2080-228 | Activity P2080-228 | Not Started | 0 | 0 | 0 | 0 | 173 | 0 | 0 | Total Float > 20 | Activity ID: P2080-228<br>Activity Name: Activity P2080-228<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 173.0
P2080-229 | Activity P2080-229 | Not Started | 0 | 0 | 0 | 0 | 304 | 0 | 0 | Total Float > 20 | Activity ID: P2080-229<br>Activity Name: Activity P2080-229<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 304.0
P2080-230 | Activity P2080-230 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-230<br>Activity Name: Activity P2080-230<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-231 | Activity P2080-231 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-231<br>Activity Name: Activity P2080-231<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-232 | Activity P2080-232 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-232<br>Activity Name: Activity P2080-232<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-233 | Activity P2080-233 | Not Started | 0 | 0 | 0 | 0 | 735 | 0 | 0 | Total Float > 20 | Activity ID: P2080-233<br>Activity Name: Activity P2080-233<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 735.0
P2080-234 | Activity P2080-234 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-234<br>Activity Name: Activity P2080-234<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-235 | Activity P2080-235 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-235<br>Activity Name: Activity P2080-235<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-236 | Activity P2080-236 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-236<br>Activity Name: Activity P2080-236<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-237 | Activity P2080-237 | Not Started | 0 | 0 | 0 | 0 | 803 | 0 | 0 | Total Float > 20 | Activity ID: P2080-237<br>Activity Name: Activity P2080-237<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 803.0
P2080-238 | Activity P2080-238 | Not Started | 0 | 0 | 0 | 0 | 803 | 0 | 0 | Total Float > 20 | Activity ID: P2080-238<br>Activity Name: Activity P2080-238<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 803.0
P2080-240 | Activity P2080-240 | Not Started | 0 | 0 | 0 | 0 | 26 | 0 | 0 | Total Float > 20 | Activity ID: P2080-240<br>Activity Name: Activity P2080-240<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 26.0
P2080-241 | Activity P2080-241 | Not Started | 0 | 0 | 0 | 0 | 376 | 0 | 0 | Total Float > 20 | Activity ID: P2080-241<br>Activity Name: Activity P2080-241<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 376.0
P2080-243 | Activity P2080-243 | Not Started | 0 | 0 | 0 | 0 | 45 | 0 | 0 | Total Float > 20 | Activity ID: P2080-243<br>Activity Name: Activity P2080-243<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 45.0
P2080-244 | Activity P2080-244 | Not Started | 0 | 0 | 0 | 0 | 84 | 0 | 0 | Total Float > 20 | Activity ID: P2080-244<br>Activity Name: Activity P2080-244<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 84.0
P2080-247 | Activity P2080-247 | Not Started | 0 | 0 | 0 | 0 | 34 | 0 | 0 | Total Float > 20 | Activity ID: P2080-247<br>Activity Name: Activity P2080-247<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 34.0
P2080-248 | Activity P2080-248 | Not Started | 0 | 0 | 0 | 0 | 84 | 0 | 0 | Total Float > 20 | Activity ID: P2080-248<br>Activity Name: Activity P2080-248<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 84.0
P2080-252 | Activity P2080-252 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-252<br>Activity Name: Activity P2080-252<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-253 | Activity P2080-253 | Not Started | 0 | 0 | 0 | 0 | 36 | 0 | 0 | Total Float > 20 | Activity ID: P2080-253<br>Activity Name: Activity P2080-253<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 36.0
P2080-254 | Activity P2080-254 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-254<br>Activity Name: Activity P2080-254<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-255 | Activity P2080-255 | Not Started | 0 | 0 | 0 | 0 | 41 | 0 | 0 | Total Float > 20 | Activity ID: P2080-255<br>Activity Name: Activity P2080-255<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 41.0
P2080-257 | Activity P2080-257 | Not Started | 0 | 0 | 0 | 0 | 44 | 0 | 0 | Total Float > 20 | Activity ID: P2080-257<br>Activity Name: Activity P2080-257<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 44.0
P2080-258 | Activity P2080-258 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-258<br>Activity Name: Activity P2080-258<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-259 | Activity P2080-259 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-259<br>Activity Name: Activity P2080-259<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-261 | Activity P2080-261 | Not Started | 0 | 0 | 0 | 0 | 304 | 0 | 0 | Total Float > 20 | Activity ID: P2080-261<br>Activity Name: Activity P2080-261<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 304.0
P2080-264 | Activity P2080-264 | Not Started | 0 | 0 | 0 | 0 | 53 | 0 | 0 | Total Float > 20 | Activity ID: P2080-264<br>Activity Name: Activity P2080-264<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 53.0
P2080-265 | Activity P2080-265 | Not Started | 0 | 0 | 0 | 0 | 431 | 0 | 0 | Total Float > 20 | Activity ID: P2080-265<br>Activity Name: Activity P2080-265<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 431.0
P2080-266 | Activity P2080-266 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-266<br>Activity Name: Activity P2080-266<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-267 | Activity P2080-267 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-267<br>Activity Name: Activity P2080-267<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-268 | Activity P2080-268 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-268<br>Activity Name: Activity P2080-268<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-269 | Activity P2080-269 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-269<br>Activity Name: Activity P2080-269<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-270 | Activity P2080-270 | Not Started | 0 | 0 | 0 | 0 | 80 | 0 | 0 | Total Float > 20 | Activity ID: P2080-270<br>Activity Name: Activity P2080-270<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 80.0
P2080-271 | Activity P2080-271 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-271<br>Activity Name: Activity P2080-271<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-272 | Activity P2080-272 | Not Started | 0 | 0 | 0 | 0 | 727 | 0 | 0 | Total Float > 20 | Activity ID: P2080-272<br>Activity Name: Activity P2080-272<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 727.0
P2080-274 | Activity P2080-274 | Not Started | 0 | 0 | 0 | 0 | 23 | 0 | 0 | Total Float > 20 | Activity ID: P2080-274<br>Activity Name: Activity P2080-274<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 23.0
P2080-275 | Activity P2080-275 | Not Started | 0 | 0 | 0 | 0 | 28 | 0 | 0 | Total Float > 20 | Activity ID: P2080-275<br>Activity Name: Activity P2080-275<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 28.0
P2080-276 | Activity P2080-276 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-276<br>Activity Name: Activity P2080-276<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-277 | Activity P2080-277 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-277<br>Activity Name: Activity P2080-277<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-278 | Activity P2080-278 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-278<br>Activity Name: Activity P2080-278<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-279 | Activity P2080-279 | Not Started | 0 | 0 | 0 | 0 | 31 | 0 | 0 | Total Float > 20 | Activity ID: P2080-279<br>Activity Name: Activity P2080-279<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 31.0
P2080-280 | Activity P2080-280 | Not Started | 0 | 0 | 0 | 0 | 55 | 0 | 0 | Total Float > 20 | Activity ID: P2080-280<br>Activity Name: Activity P2080-280<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 55.0
P2080-281 | Activity P2080-281 | Not Started | 0 | 0 | 0 | 0 | 36 | 0 | 0 | Total Float > 20 | Activity ID: P2080-281<br>Activity Name: Activity P2080-281<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 36.0
P2080-282 | Activity P2080-282 | Not Started | 0 | 0 | 0 | 0 | 47 | 0 | 0 | Total Float > 20 | Activity ID: P2080-282<br>Activity Name: Activity P2080-282<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 47.0
P2080-283 | Activity P2080-283 | Not Started | 0 | 0 | 0 | 0 | 55 | 0 | 0 | Total Float > 20 | Activity ID: P2080-283<br>Activity Name: Activity P2080-283<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 55.0
P2080-284 | Activity P2080-284 | Not Started | 0 | 0 | 0 | 0 | 84 | 0 | 0 | Total Float > 20 | Activity ID: P2080-284<br>Activity Name: Activity P2080-284<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 84.0
P2080-287 | Activity P2080-287 | Not Started | 0 | 0 | 0 | 0 | 100 | 0 | 0 | Total Float > 20 | Activity ID: P2080-287<br>Activity Name: Activity P2080-287<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 100.0
P2080-288 | Activity P2080-288 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-288<br>Activity Name: Activity P2080-288<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-289 | Activity P2080-289 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-289<br>Activity Name: Activity P2080-289<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-290 | Activity P2080-290 | Not Started | 0 | 0 | 0 | 0 | 129 | 0 | 0 | Total Float > 20 | Activity ID: P2080-290<br>Activity Name: Activity P2080-290<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 129.0
P2080-291 | Activity P2080-291 | Not Started | 0 | 0 | 0 | 0 | 821 | 0 | 0 | Total Float > 20 | Activity ID: P2080-291<br>Activity Name: Activity P2080-291<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 821.0
P2080-292 | Activity P2080-292 | Not Started | 0 | 0 | 0 | 0 | 38 | 0 | 0 | Total Float > 20 | Activity ID: P2080-292<br>Activity Name: Activity P2080-292<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 38.0
P2080-293 | Activity P2080-293 | Not Started | 0 | 0 | 0 | 0 | 45 | 0 | 0 | Total Float > 20 | Activity ID: P2080-293<br>Activity Name: Activity P2080-293<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 45.0
P2080-294 | Activity P2080-294 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-294<br>Activity Name: Activity P2080-294<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-297 | Activity P2080-297 | Not Started | 0 | 0 | 0 | 0 | 32 | 0 | 0 | Total Float > 20 | Activity ID: P2080-297<br>Activity Name: Activity P2080-297<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 32.0
P2080-298 | Activity P2080-298 | Not Started | 0 | 0 | 0 | 0 | 45 | 0 | 0 | Total Float > 20 | Activity ID: P2080-298<br>Activity Name: Activity P2080-298<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 45.0
P2080-299 | Activity P2080-299 | Not Started | 0 | 0 | 0 | 0 | 66 | 0 | 0 | Total Float > 20 | Activity ID: P2080-299<br>Activity Name: Activity P2080-299<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 66.0
P2080-300 | Activity P2080-300 | Not Started | 0 | 0 | 0 | 0 | 70 | 0 | 0 | Total Float > 20 | Activity ID: P2080-300<br>Activity Name: Activity P2080-300<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 70.0
P2080-301 | Activity P2080-301 | Not Started | 0 | 0 | 0 | 0 | 26 | 0 | 0 | Total Float > 20 | Activity ID: P2080-301<br>Activity Name: Activity P2080-301<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 26.0
P2080-302 | Activity P2080-302 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-302<br>Activity Name: Activity P2080-302<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-303 | Activity P2080-303 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-303<br>Activity Name: Activity P2080-303<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-304 | Activity P2080-304 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-304<br>Activity Name: Activity P2080-304<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-305 | Activity P2080-305 | Not Started | 0 | 0 | 0 | 0 | 34 | 0 | 0 | Total Float > 20 | Activity ID: P2080-305<br>Activity Name: Activity P2080-305<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 34.0
P2080-306 | Activity P2080-306 | Not Started | 0 | 0 | 0 | 0 | 44 | 0 | 0 | Total Float > 20 | Activity ID: P2080-306<br>Activity Name: Activity P2080-306<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 44.0
P2080-307 | Activity P2080-307 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-307<br>Activity Name: Activity P2080-307<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-308 | Activity P2080-308 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-308<br>Activity Name: Activity P2080-308<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-310 | Activity P2080-310 | Not Started | 0 | 0 | 0 | 0 | 719 | 0 | 0 | Total Float > 20 | Activity ID: P2080-310<br>Activity Name: Activity P2080-310<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 719.0
P2080-311 | Activity P2080-311 | Not Started | 0 | 0 | 0 | 0 | 719 | 0 | 0 | Total Float > 20 | Activity ID: P2080-311<br>Activity Name: Activity P2080-311<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 719.0
P2080-314 | Activity P2080-314 | Not Started | 0 | 0 | 0 | 0 | 42 | 0 | 0 | Total Float > 20 | Activity ID: P2080-314<br>Activity Name: Activity P2080-314<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 42.0
P2080-316 | Activity P2080-316 | Not Started | 0 | 0 | 0 | 0 | 52 | 0 | 0 | Total Float > 20 | Activity ID: P2080-316<br>Activity Name: Activity P2080-316<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 52.0
P2080-317 | Activity P2080-317 | Not Started | 0 | 0 | 0 | 0 | 67 | 0 | 0 | Total Float > 20 | Activity ID: P2080-317<br>Activity Name: Activity P2080-317<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 67.0
P2080-323 | Activity P2080-323 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-323<br>Activity Name: Activity P2080-323<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-325 | Activity P2080-325 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-325<br>Activity Name: Activity P2080-325<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-326 | Activity P2080-326 | Not Started | 0 | 0 | 0 | 0 | 149 | 0 | 0 | Total Float > 20 | Activity ID: P2080-326<br>Activity Name: Activity P2080-326<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 149.0
P2080-327 | Activity P2080-327 | Not Started | 0 | 0 | 0 | 0 | 34 | 0 | 0 | Total Float > 20 | Activity ID: P2080-327<br>Activity Name: Activity P2080-327<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 34.0
P2080-329 | Activity P2080-329 | Not Started | 0 | 0 | 0 | 0 | 107 | 0 | 0 | Total Float > 20 | Activity ID: P2080-329<br>Activity Name: Activity P2080-329<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 107.0
P2080-330 | Activity P2080-330 | Not Started | 0 | 0 | 0 | 0 | 107 | 0 | 0 | Total Float > 20 | Activity ID: P2080-330<br>Activity Name: Activity P2080-330<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 107.0
P2080-331 | Activity P2080-331 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-331<br>Activity Name: Activity P2080-331<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-332 | Activity P2080-332 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-332<br>Activity Name: Activity P2080-332<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-333 | Activity P2080-333 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-333<br>Activity Name: Activity P2080-333<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-334 | Activity P2080-334 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-334<br>Activity Name: Activity P2080-334<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-335 | Activity P2080-335 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-335<br>Activity Name: Activity P2080-335<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-336 | Activity P2080-336 | Not Started | 0 | 0 | 0 | 0 | 48 | 0 | 0 | Total Float > 20 | Activity ID: P2080-336<br>Activity Name: Activity P2080-336<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 48.0
P2080-338 | Activity P2080-338 | Not Started | 0 | 0 | 0 | 0 | 44 | 0 | 0 | Total Float > 20 | Activity ID: P2080-338<br>Activity Name: Activity P2080-338<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 44.0
P2080-339 | Activity P2080-339 | Not Started | 0 | 0 | 0 | 0 | 107 | 0 | 0 | Total Float > 20 | Activity ID: P2080-339<br>Activity Name: Activity P2080-339<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 107.0
P2080-340 | Activity P2080-340 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-340<br>Activity Name: Activity P2080-340<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-341 | Activity P2080-341 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-341<br>Activity Name: Activity P2080-341<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-343 | Activity P2080-343 | Not Started | 0 | 0 | 0 | 0 | 711 | 0 | 0 | Total Float > 20 | Activity ID: P2080-343<br>Activity Name: Activity P2080-343<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 711.0
P2080-344 | Activity P2080-344 | Not Started | 0 | 0 | 0 | 0 | 34 | 0 | 0 | Total Float > 20 | Activity ID: P2080-344<br>Activity Name: Activity P2080-344<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 34.0
P2080-345 | Activity P2080-345 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-345<br>Activity Name: Activity P2080-345<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-346 | Activity P2080-346 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-346<br>Activity Name: Activity P2080-346<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-350 | Activity P2080-350 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-350<br>Activity Name: Activity P2080-350<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-351 | Activity P2080-351 | Not Started | 0 | 0 | 0 | 0 | 46 | 0 | 0 | Total Float > 20 | Activity ID: P2080-351<br>Activity Name: Activity P2080-351<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 46.0
P2080-353 | Activity P2080-353 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-353<br>Activity Name: Activity P2080-353<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-354 | Activity P2080-354 | Not Started | 0 | 0 | 0 | 0 | 108 | 0 | 0 | Total Float > 20 | Activity ID: P2080-354<br>Activity Name: Activity P2080-354<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 108.0
P2080-355 | Activity P2080-355 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-355<br>Activity Name: Activity P2080-355<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-356 | Activity P2080-356 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-356<br>Activity Name: Activity P2080-356<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-357 | Activity P2080-357 | Not Started | 0 | 0 | 0 | 0 | 34 | 0 | 0 | Total Float > 20 | Activity ID: P2080-357<br>Activity Name: Activity P2080-357<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 34.0
P2080-358 | Activity P2080-358 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-358<br>Activity Name: Activity P2080-358<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-359 | Activity P2080-359 | Not Started | 0 | 0 | 0 | 0 | 108 | 0 | 0 | Total Float > 20 | Activity ID: P2080-359<br>Activity Name: Activity P2080-359<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 108.0
P2080-360 | Activity P2080-360 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-360<br>Activity Name: Activity P2080-360<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-361 | Activity P2080-361 | Not Started | 0 | 0 | 0 | 0 | 108 | 0 | 0 | Total Float > 20 | Activity ID: P2080-361<br>Activity Name: Activity P2080-361<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 108.0
P2080-364 | Activity P2080-364 | Not Started | 0 | 0 | 0 | 0 | 67 | 0 | 0 | Total Float > 20 | Activity ID: P2080-364<br>Activity Name: Activity P2080-364<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 67.0
P2080-365 | Activity P2080-365 | Not Started | 0 | 0 | 0 | 0 | 45 | 0 | 0 | Total Float > 20 | Activity ID: P2080-365<br>Activity Name: Activity P2080-365<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 45.0
P2080-366 | Activity P2080-366 | Not Started | 0 | 0 | 0 | 0 | 52 | 0 | 0 | Total Float > 20 | Activity ID: P2080-366<br>Activity Name: Activity P2080-366<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 52.0
P2080-367 | Activity P2080-367 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-367<br>Activity Name: Activity P2080-367<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-368 | Activity P2080-368 | Not Started | 0 | 0 | 0 | 0 | 55 | 0 | 0 | Total Float > 20 | Activity ID: P2080-368<br>Activity Name: Activity P2080-368<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 55.0
P2080-369 | Activity P2080-369 | Not Started | 0 | 0 | 0 | 0 | 55 | 0 | 0 | Total Float > 20 | Activity ID: P2080-369<br>Activity Name: Activity P2080-369<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 55.0
P2080-370 | Activity P2080-370 | Not Started | 0 | 0 | 0 | 0 | 64 | 0 | 0 | Total Float > 20 | Activity ID: P2080-370<br>Activity Name: Activity P2080-370<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 64.0
P2080-371 | Activity P2080-371 | Not Started | 0 | 0 | 0 | 0 | 64 | 0 | 0 | Total Float > 20 | Activity ID: P2080-371<br>Activity Name: Activity P2080-371<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 64.0
P2080-372 | Activity P2080-372 | Not Started | 0 | 0 | 0 | 0 | 64 | 0 | 0 | Total Float > 20 | Activity ID: P2080-372<br>Activity Name: Activity P2080-372<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 64.0
P2080-373 | Activity P2080-373 | Not Started | 0 | 0 | 0 | 0 | 64 | 0 | 0 | Total Float > 20 | Activity ID: P2080-373<br>Activity Name: Activity P2080-373<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 64.0
P2080-374 | Activity P2080-374 | Not Started | 0 | 0 | 0 | 0 | 104 | 0 | 0 | Total Float > 20 | Activity ID: P2080-374<br>Activity Name: Activity P2080-374<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 104.0
P2080-375 | Activity P2080-375 | Not Started | 0 | 0 | 0 | 0 | 104 | 0 | 0 | Total Float > 20 | Activity ID: P2080-375<br>Activity Name: Activity P2080-375<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 104.0
P2080-376 | Activity P2080-376 | Not Started | 0 | 0 | 0 | 0 | 104 | 0 | 0 | Total Float > 20 | Activity ID: P2080-376<br>Activity Name: Activity P2080-376<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 104.0
P2080-377 | Activity P2080-377 | Not Started | 0 | 0 | 0 | 0 | 104 | 0 | 0 | Total Float > 20 | Activity ID: P2080-377<br>Activity Name: Activity P2080-377<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 104.0
P2080-378 | Activity P2080-378 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-378<br>Activity Name: Activity P2080-378<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-379 | Activity P2080-379 | Not Started | 0 | 0 | 0 | 0 | 157 | 0 | 0 | Total Float > 20 | Activity ID: P2080-379<br>Activity Name: Activity P2080-379<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 157.0
P2080-380 | Activity P2080-380 | Not Started | 0 | 0 | 0 | 0 | 157 | 0 | 0 | Total Float > 20 | Activity ID: P2080-380<br>Activity Name: Activity P2080-380<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 157.0
P2080-381 | Activity P2080-381 | Not Started | 0 | 0 | 0 | 0 | 165 | 0 | 0 | Total Float > 20 | Activity ID: P2080-381<br>Activity Name: Activity P2080-381<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 165.0
P2080-382 | Activity P2080-382 | Not Started | 0 | 0 | 0 | 0 | 165 | 0 | 0 | Total Float > 20 | Activity ID: P2080-382<br>Activity Name: Activity P2080-382<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 165.0
P2080-383 | Activity P2080-383 | Not Started | 0 | 0 | 0 | 0 | 173 | 0 | 0 | Total Float > 20 | Activity ID: P2080-383<br>Activity Name: Activity P2080-383<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 173.0
P2080-384 | Activity P2080-384 | Not Started | 0 | 0 | 0 | 0 | 173 | 0 | 0 | Total Float > 20 | Activity ID: P2080-384<br>Activity Name: Activity P2080-384<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 173.0
P2080-385 | Activity P2080-385 | Not Started | 0 | 0 | 0 | 0 | 705 | 0 | 0 | Total Float > 20 | Activity ID: P2080-385<br>Activity Name: Activity P2080-385<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 705.0
P2080-386 | Activity P2080-386 | Not Started | 0 | 0 | 0 | 0 | 801 | 0 | 0 | Total Float > 20 | Activity ID: P2080-386<br>Activity Name: Activity P2080-386<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 801.0
P2080-391 | Activity P2080-391 | Not Started | 0 | 0 | 0 | 0 | 40 | 0 | 0 | Total Float > 20 | Activity ID: P2080-391<br>Activity Name: Activity P2080-391<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 40.0
P2080-392 | Activity P2080-392 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-392<br>Activity Name: Activity P2080-392<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-394 | Activity P2080-394 | Not Started | 0 | 0 | 0 | 0 | 149 | 0 | 0 | Total Float > 20 | Activity ID: P2080-394<br>Activity Name: Activity P2080-394<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 149.0
P2080-395 | Activity P2080-395 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-395<br>Activity Name: Activity P2080-395<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-396 | Activity P2080-396 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-396<br>Activity Name: Activity P2080-396<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-397 | Activity P2080-397 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-397<br>Activity Name: Activity P2080-397<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-399 | Activity P2080-399 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-399<br>Activity Name: Activity P2080-399<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-400 | Activity P2080-400 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-400<br>Activity Name: Activity P2080-400<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-401 | Activity P2080-401 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-401<br>Activity Name: Activity P2080-401<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-402 | Activity P2080-402 | Not Started | 0 | 0 | 0 | 0 | 108 | 0 | 0 | Total Float > 20 | Activity ID: P2080-402<br>Activity Name: Activity P2080-402<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 108.0
P2080-404 | Activity P2080-404 | Not Started | 0 | 0 | 0 | 0 | 32 | 0 | 0 | Total Float > 20 | Activity ID: P2080-404<br>Activity Name: Activity P2080-404<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 32.0
P2080-405 | Activity P2080-405 | Not Started | 0 | 0 | 0 | 0 | 696 | 0 | 0 | Total Float > 20 | Activity ID: P2080-405<br>Activity Name: Activity P2080-405<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 696.0
P2080-406 | Activity P2080-406 | Not Started | 0 | 0 | 0 | 0 | 696 | 0 | 0 | Total Float > 20 | Activity ID: P2080-406<br>Activity Name: Activity P2080-406<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 696.0
P2080-410 | Activity P2080-410 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-410<br>Activity Name: Activity P2080-410<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-411 | Activity P2080-411 | Not Started | 0 | 0 | 0 | 0 | 93 | 0 | 0 | Total Float > 20 | Activity ID: P2080-411<br>Activity Name: Activity P2080-411<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 93.0
P2080-412 | Activity P2080-412 | Not Started | 0 | 0 | 0 | 0 | 27 | 0 | 0 | Total Float > 20 | Activity ID: P2080-412<br>Activity Name: Activity P2080-412<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 27.0
P2080-413 | Activity P2080-413 | Not Started | 0 | 0 | 0 | 0 | 155 | 0 | 0 | Total Float > 20 | Activity ID: P2080-413<br>Activity Name: Activity P2080-413<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 155.0
P2080-414 | Activity P2080-414 | Not Started | 0 | 0 | 0 | 0 | 67 | 0 | 0 | Total Float > 20 | Activity ID: P2080-414<br>Activity Name: Activity P2080-414<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 67.0
P2080-415 | Activity P2080-415 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-415<br>Activity Name: Activity P2080-415<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-416 | Activity P2080-416 | Not Started | 0 | 0 | 0 | 0 | 129 | 0 | 0 | Total Float > 20 | Activity ID: P2080-416<br>Activity Name: Activity P2080-416<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 129.0
P2080-417 | Activity P2080-417 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-417<br>Activity Name: Activity P2080-417<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-418 | Activity P2080-418 | Not Started | 0 | 0 | 0 | 0 | 281 | 0 | 0 | Total Float > 20 | Activity ID: P2080-418<br>Activity Name: Activity P2080-418<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 281.0
P2080-420 | Activity P2080-420 | Not Started | 0 | 0 | 0 | 0 | 45 | 0 | 0 | Total Float > 20 | Activity ID: P2080-420<br>Activity Name: Activity P2080-420<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 45.0
P2080-421 | Activity P2080-421 | Not Started | 0 | 0 | 0 | 0 | 52 | 0 | 0 | Total Float > 20 | Activity ID: P2080-421<br>Activity Name: Activity P2080-421<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 52.0
P2080-423 | Activity P2080-423 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-423<br>Activity Name: Activity P2080-423<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-424 | Activity P2080-424 | Not Started | 0 | 0 | 0 | 0 | 38 | 0 | 0 | Total Float > 20 | Activity ID: P2080-424<br>Activity Name: Activity P2080-424<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 38.0
P2080-425 | Activity P2080-425 | Not Started | 0 | 0 | 0 | 0 | 129 | 0 | 0 | Total Float > 20 | Activity ID: P2080-425<br>Activity Name: Activity P2080-425<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 129.0
P2080-426 | Activity P2080-426 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-426<br>Activity Name: Activity P2080-426<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-427 | Activity P2080-427 | Not Started | 0 | 0 | 0 | 0 | 787 | 0 | 0 | Total Float > 20 | Activity ID: P2080-427<br>Activity Name: Activity P2080-427<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 787.0
P2080-428 | Activity P2080-428 | Not Started | 0 | 0 | 0 | 0 | 204 | 0 | 0 | Total Float > 20 | Activity ID: P2080-428<br>Activity Name: Activity P2080-428<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 204.0
P2080-429 | Activity P2080-429 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-429<br>Activity Name: Activity P2080-429<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-430 | Activity P2080-430 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-430<br>Activity Name: Activity P2080-430<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-432 | Activity P2080-432 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-432<br>Activity Name: Activity P2080-432<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-434 | Activity P2080-434 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-434<br>Activity Name: Activity P2080-434<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-435 | Activity P2080-435 | Not Started | 0 | 0 | 0 | 0 | 129 | 0 | 0 | Total Float > 20 | Activity ID: P2080-435<br>Activity Name: Activity P2080-435<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 129.0
P2080-436 | Activity P2080-436 | Not Started | 0 | 0 | 0 | 0 | 105 | 0 | 0 | Total Float > 20 | Activity ID: P2080-436<br>Activity Name: Activity P2080-436<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 105.0
P2080-437 | Activity P2080-437 | Not Started | 0 | 0 | 0 | 0 | 785 | 0 | 0 | Total Float > 20 | Activity ID: P2080-437<br>Activity Name: Activity P2080-437<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 785.0
P2080-438 | Activity P2080-438 | Not Started | 0 | 0 | 0 | 0 | 181 | 0 | 0 | Total Float > 20 | Activity ID: P2080-438<br>Activity Name: Activity P2080-438<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 181.0
P2080-440 | Activity P2080-440 | Not Started | 0 | 0 | 0 | 0 | 88 | 0 | 0 | Total Float > 20 | Activity ID: P2080-440<br>Activity Name: Activity P2080-440<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 88.0
P2080-441 | Activity P2080-441 | Not Started | 0 | 0 | 0 | 0 | 123 | 0 | 0 | Total Float > 20 | Activity ID: P2080-441<br>Activity Name: Activity P2080-441<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 123.0
P2080-442 | Activity P2080-442 | Not Started | 0 | 0 | 0 | 0 | 31 | 0 | 0 | Total Float > 20 | Activity ID: P2080-442<br>Activity Name: Activity P2080-442<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 31.0
P2080-444 | Activity P2080-444 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-444<br>Activity Name: Activity P2080-444<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-445 | Activity P2080-445 | Not Started | 0 | 0 | 0 | 0 | 146 | 0 | 0 | Total Float > 20 | Activity ID: P2080-445<br>Activity Name: Activity P2080-445<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 146.0
P2080-446 | Activity P2080-446 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-446<br>Activity Name: Activity P2080-446<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-447 | Activity P2080-447 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-447<br>Activity Name: Activity P2080-447<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-449 | Activity P2080-449 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-449<br>Activity Name: Activity P2080-449<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-450 | Activity P2080-450 | Not Started | 0 | 0 | 0 | 0 | 113 | 0 | 0 | Total Float > 20 | Activity ID: P2080-450<br>Activity Name: Activity P2080-450<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 113.0
P2080-451 | Activity P2080-451 | Not Started | 0 | 0 | 0 | 0 | 113 | 0 | 0 | Total Float > 20 | Activity ID: P2080-451<br>Activity Name: Activity P2080-451<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 113.0
P2080-454 | Activity P2080-454 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-454<br>Activity Name: Activity P2080-454<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-455 | Activity P2080-455 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-455<br>Activity Name: Activity P2080-455<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-456 | Activity P2080-456 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-456<br>Activity Name: Activity P2080-456<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-457 | Activity P2080-457 | Not Started | 0 | 0 | 0 | 0 | 129 | 0 | 0 | Total Float > 20 | Activity ID: P2080-457<br>Activity Name: Activity P2080-457<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 129.0
P2080-458 | Activity P2080-458 | Not Started | 0 | 0 | 0 | 0 | 134 | 0 | 0 | Total Float > 20 | Activity ID: P2080-458<br>Activity Name: Activity P2080-458<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 134.0
P2080-459 | Activity P2080-459 | Not Started | 0 | 0 | 0 | 0 | 41 | 0 | 0 | Total Float > 20 | Activity ID: P2080-459<br>Activity Name: Activity P2080-459<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 41.0
P2080-460 | Activity P2080-460 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-460<br>Activity Name: Activity P2080-460<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-461 | Activity P2080-461 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-461<br>Activity Name: Activity P2080-461<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-462 | Activity P2080-462 | Not Started | 0 | 0 | 0 | 0 | 87 | 0 | 0 | Total Float > 20 | Activity ID: P2080-462<br>Activity Name: Activity P2080-462<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 87.0
P2080-463 | Activity P2080-463 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-463<br>Activity Name: Activity P2080-463<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-464 | Activity P2080-464 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-464<br>Activity Name: Activity P2080-464<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-466 | Activity P2080-466 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-466<br>Activity Name: Activity P2080-466<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-467 | Activity P2080-467 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-467<br>Activity Name: Activity P2080-467<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-468 | Activity P2080-468 | Not Started | 0 | 0 | 0 | 0 | 129 | 0 | 0 | Total Float > 20 | Activity ID: P2080-468<br>Activity Name: Activity P2080-468<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 129.0
P2080-469 | Activity P2080-469 | Not Started | 0 | 0 | 0 | 0 | 771 | 0 | 0 | Total Float > 20 | Activity ID: P2080-469<br>Activity Name: Activity P2080-469<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 771.0
P2080-470 | Activity P2080-470 | Not Started | 0 | 0 | 0 | 0 | 771 | 0 | 0 | Total Float > 20 | Activity ID: P2080-470<br>Activity Name: Activity P2080-470<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 771.0
P2080-471 | Activity P2080-471 | Not Started | 0 | 0 | 0 | 0 | 34 | 0 | 0 | Total Float > 20 | Activity ID: P2080-471<br>Activity Name: Activity P2080-471<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 34.0
P2080-472 | Activity P2080-472 | Not Started | 0 | 0 | 0 | 0 | 34 | 0 | 0 | Total Float > 20 | Activity ID: P2080-472<br>Activity Name: Activity P2080-472<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 34.0
P2080-473 | Activity P2080-473 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-473<br>Activity Name: Activity P2080-473<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-474 | Activity P2080-474 | Not Started | 0 | 0 | 0 | 0 | 87 | 0 | 0 | Total Float > 20 | Activity ID: P2080-474<br>Activity Name: Activity P2080-474<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 87.0
P2080-475 | Activity P2080-475 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-475<br>Activity Name: Activity P2080-475<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-476 | Activity P2080-476 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-476<br>Activity Name: Activity P2080-476<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-477 | Activity P2080-477 | Not Started | 0 | 0 | 0 | 0 | 46 | 0 | 0 | Total Float > 20 | Activity ID: P2080-477<br>Activity Name: Activity P2080-477<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 46.0
P2080-480 | Activity P2080-480 | Not Started | 0 | 0 | 0 | 0 | 129 | 0 | 0 | Total Float > 20 | Activity ID: P2080-480<br>Activity Name: Activity P2080-480<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 129.0
P2080-482 | Activity P2080-482 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-482<br>Activity Name: Activity P2080-482<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-483 | Activity P2080-483 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-483<br>Activity Name: Activity P2080-483<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-484 | Activity P2080-484 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-484<br>Activity Name: Activity P2080-484<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-486 | Activity P2080-486 | Not Started | 0 | 0 | 0 | 0 | 47 | 0 | 0 | Total Float > 20 | Activity ID: P2080-486<br>Activity Name: Activity P2080-486<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 47.0
P2080-487 | Activity P2080-487 | Not Started | 0 | 0 | 0 | 0 | 54 | 0 | 0 | Total Float > 20 | Activity ID: P2080-487<br>Activity Name: Activity P2080-487<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 54.0
P2080-489 | Activity P2080-489 | Not Started | 0 | 0 | 0 | 0 | 38 | 0 | 0 | Total Float > 20 | Activity ID: P2080-489<br>Activity Name: Activity P2080-489<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 38.0
P2080-490 | Activity P2080-490 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-490<br>Activity Name: Activity P2080-490<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-491 | Activity P2080-491 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-491<br>Activity Name: Activity P2080-491<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-492 | Activity P2080-492 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-492<br>Activity Name: Activity P2080-492<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-493 | Activity P2080-493 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-493<br>Activity Name: Activity P2080-493<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-494 | Activity P2080-494 | Not Started | 0 | 0 | 0 | 0 | 113 | 0 | 0 | Total Float > 20 | Activity ID: P2080-494<br>Activity Name: Activity P2080-494<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 113.0
P2080-495 | Activity P2080-495 | Not Started | 0 | 0 | 0 | 0 | 113 | 0 | 0 | Total Float > 20 | Activity ID: P2080-495<br>Activity Name: Activity P2080-495<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 113.0
P2080-496 | Activity P2080-496 | Not Started | 0 | 0 | 0 | 0 | 117 | 0 | 0 | Total Float > 20 | Activity ID: P2080-496<br>Activity Name: Activity P2080-496<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 117.0
P2080-499 | Activity P2080-499 | Not Started | 0 | 0 | 0 | 0 | 21 | 0 | 0 | Total Float > 20 | Activity ID: P2080-499<br>Activity Name: Activity P2080-499<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 21.0
P2080-500 | Activity P2080-500 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-500<br>Activity Name: Activity P2080-500<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-501 | Activity P2080-501 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-501<br>Activity Name: Activity P2080-501<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-502 | Activity P2080-502 | Not Started | 0 | 0 | 0 | 0 | 29 | 0 | 0 | Total Float > 20 | Activity ID: P2080-502<br>Activity Name: Activity P2080-502<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 29.0
P2080-503 | Activity P2080-503 | Not Started | 0 | 0 | 0 | 0 | 28 | 0 | 0 | Total Float > 20 | Activity ID: P2080-503<br>Activity Name: Activity P2080-503<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 28.0
P2080-504 | Activity P2080-504 | Not Started | 0 | 0 | 0 | 0 | 42 | 0 | 0 | Total Float > 20 | Activity ID: P2080-504<br>Activity Name: Activity P2080-504<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 42.0
P2080-506 | Activity P2080-506 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-506<br>Activity Name: Activity P2080-506<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-508 | Activity P2080-508 | Not Started | 0 | 0 | 0 | 0 | 108 | 0 | 0 | Total Float > 20 | Activity ID: P2080-508<br>Activity Name: Activity P2080-508<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 108.0
P2080-509 | Activity P2080-509 | Not Started | 0 | 0 | 0 | 0 | 757 | 0 | 0 | Total Float > 20 | Activity ID: P2080-509<br>Activity Name: Activity P2080-509<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 757.0
P2080-510 | Activity P2080-510 | Not Started | 0 | 0 | 0 | 0 | 661 | 0 | 0 | Total Float > 20 | Activity ID: P2080-510<br>Activity Name: Activity P2080-510<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 661.0
P2080-513 | Activity P2080-513 | Not Started | 0 | 0 | 0 | 0 | 38 | 0 | 0 | Total Float > 20 | Activity ID: P2080-513<br>Activity Name: Activity P2080-513<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 38.0
P2080-514 | Activity P2080-514 | Not Started | 0 | 0 | 0 | 0 | 38 | 0 | 0 | Total Float > 20 | Activity ID: P2080-514<br>Activity Name: Activity P2080-514<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 38.0
P2080-515 | Activity P2080-515 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-515<br>Activity Name: Activity P2080-515<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-516 | Activity P2080-516 | Not Started | 0 | 0 | 0 | 0 | 51 | 0 | 0 | Total Float > 20 | Activity ID: P2080-516<br>Activity Name: Activity P2080-516<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 51.0
P2080-517 | Activity P2080-517 | Not Started | 0 | 0 | 0 | 0 | 756 | 0 | 0 | Total Float > 20 | Activity ID: P2080-517<br>Activity Name: Activity P2080-517<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 756.0
P2080-518 | Activity P2080-518 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-518<br>Activity Name: Activity P2080-518<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-522 | Activity P2080-522 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-522<br>Activity Name: Activity P2080-522<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-523 | Activity P2080-523 | Not Started | 0 | 0 | 0 | 0 | 659 | 0 | 0 | Total Float > 20 | Activity ID: P2080-523<br>Activity Name: Activity P2080-523<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 659.0
P2080-525 | Activity P2080-525 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-525<br>Activity Name: Activity P2080-525<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-526 | Activity P2080-526 | Not Started | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Total Float > 20 | Activity ID: P2080-526<br>Activity Name: Activity P2080-526<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 24.0
P2080-527 | Activity P2080-527 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-527<br>Activity Name: Activity P2080-527<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-528 | Activity P2080-528 | Not Started | 0 | 0 | 0 | 0 | 51 | 0 | 0 | Total Float > 20 | Activity ID: P2080-528<br>Activity Name: Activity P2080-528<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 51.0
P2080-529 | Activity P2080-529 | Not Started | 0 | 0 | 0 | 0 | 68 | 0 | 0 | Total Float > 20 | Activity ID: P2080-529<br>Activity Name: Activity P2080-529<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 68.0
P2080-530 | Activity P2080-530 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-530<br>Activity Name: Activity P2080-530<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-531 | Activity P2080-531 | Not Started | 0 | 0 | 0 | 0 | 51 | 0 | 0 | Total Float > 20 | Activity ID: P2080-531<br>Activity Name: Activity P2080-531<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 51.0
P2080-532 | Activity P2080-532 | Not Started | 0 | 0 | 0 | 0 | 108 | 0 | 0 | Total Float > 20 | Activity ID: P2080-532<br>Activity Name: Activity P2080-532<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 108.0
P2080-533 | Activity P2080-533 | Not Started | 0 | 0 | 0 | 0 | 754 | 0 | 0 | Total Float > 20 | Activity ID: P2080-533<br>Activity Name: Activity P2080-533<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 754.0
P2080-534 | Activity P2080-534 | Not Started | 0 | 0 | 0 | 0 | 87 | 0 | 0 | Total Float > 20 | Activity ID: P2080-534<br>Activity Name: Activity P2080-534<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 87.0
P2080-535 | Activity P2080-535 | Not Started | 0 | 0 | 0 | 0 | 151 | 0 | 0 | Total Float > 20 | Activity ID: P2080-535<br>Activity Name: Activity P2080-535<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 151.0
P2080-537 | Activity P2080-537 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-537<br>Activity Name: Activity P2080-537<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-539 | Activity P2080-539 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-539<br>Activity Name: Activity P2080-539<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-540 | Activity P2080-540 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-540<br>Activity Name: Activity P2080-540<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-541 | Activity P2080-541 | Not Started | 0 | 0 | 0 | 0 | 154 | 0 | 0 | Total Float > 20 | Activity ID: P2080-541<br>Activity Name: Activity P2080-541<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 154.0
P2080-542 | Activity P2080-542 | Not Started | 0 | 0 | 0 | 0 | 47 | 0 | 0 | Total Float > 20 | Activity ID: P2080-542<br>Activity Name: Activity P2080-542<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 47.0
P2080-543 | Activity P2080-543 | Not Started | 0 | 0 | 0 | 0 | 54 | 0 | 0 | Total Float > 20 | Activity ID: P2080-543<br>Activity Name: Activity P2080-543<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 54.0
P2080-546 | Activity P2080-546 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-546<br>Activity Name: Activity P2080-546<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-547 | Activity P2080-547 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-547<br>Activity Name: Activity P2080-547<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-549 | Activity P2080-549 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-549<br>Activity Name: Activity P2080-549<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-550 | Activity P2080-550 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-550<br>Activity Name: Activity P2080-550<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-551 | Activity P2080-551 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-551<br>Activity Name: Activity P2080-551<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-552 | Activity P2080-552 | Not Started | 0 | 0 | 0 | 0 | 748 | 0 | 0 | Total Float > 20 | Activity ID: P2080-552<br>Activity Name: Activity P2080-552<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 748.0
P2080-553 | Activity P2080-553 | Not Started | 0 | 0 | 0 | 0 | 143 | 0 | 0 | Total Float > 20 | Activity ID: P2080-553<br>Activity Name: Activity P2080-553<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 143.0
P2080-554 | Activity P2080-554 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-554<br>Activity Name: Activity P2080-554<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-557 | Activity P2080-557 | Not Started | 0 | 0 | 0 | 0 | 48 | 0 | 0 | Total Float > 20 | Activity ID: P2080-557<br>Activity Name: Activity P2080-557<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 48.0
P2080-559 | Activity P2080-559 | Not Started | 0 | 0 | 0 | 0 | 38 | 0 | 0 | Total Float > 20 | Activity ID: P2080-559<br>Activity Name: Activity P2080-559<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 38.0
P2080-560 | Activity P2080-560 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-560<br>Activity Name: Activity P2080-560<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-561 | Activity P2080-561 | Not Started | 0 | 0 | 0 | 0 | 746 | 0 | 0 | Total Float > 20 | Activity ID: P2080-561<br>Activity Name: Activity P2080-561<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 746.0
P2080-562 | Activity P2080-562 | Not Started | 0 | 0 | 0 | 0 | 236 | 0 | 0 | Total Float > 20 | Activity ID: P2080-562<br>Activity Name: Activity P2080-562<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 236.0
P2080-571 | Activity P2080-571 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-571<br>Activity Name: Activity P2080-571<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-572 | Activity P2080-572 | Not Started | 0 | 0 | 0 | 0 | 48 | 0 | 0 | Total Float > 20 | Activity ID: P2080-572<br>Activity Name: Activity P2080-572<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 48.0
P2080-573 | Activity P2080-573 | Not Started | 0 | 0 | 0 | 0 | 105 | 0 | 0 | Total Float > 20 | Activity ID: P2080-573<br>Activity Name: Activity P2080-573<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 105.0
P2080-574 | Activity P2080-574 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-574<br>Activity Name: Activity P2080-574<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-575 | Activity P2080-575 | Not Started | 0 | 0 | 0 | 0 | 107 | 0 | 0 | Total Float > 20 | Activity ID: P2080-575<br>Activity Name: Activity P2080-575<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 107.0
P2080-576 | Activity P2080-576 | Not Started | 0 | 0 | 0 | 0 | 236 | 0 | 0 | Total Float > 20 | Activity ID: P2080-576<br>Activity Name: Activity P2080-576<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 236.0
P2080-577 | Activity P2080-577 | Not Started | 0 | 0 | 0 | 0 | 719 | 0 | 0 | Total Float > 20 | Activity ID: P2080-577<br>Activity Name: Activity P2080-577<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 719.0
P2080-578 | Activity P2080-578 | Not Started | 0 | 0 | 0 | 0 | 745 | 0 | 0 | Total Float > 20 | Activity ID: P2080-578<br>Activity Name: Activity P2080-578<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 745.0
P2080-579 | Activity P2080-579 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-579<br>Activity Name: Activity P2080-579<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-580 | Activity P2080-580 | Not Started | 0 | 0 | 0 | 0 | 51 | 0 | 0 | Total Float > 20 | Activity ID: P2080-580<br>Activity Name: Activity P2080-580<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 51.0
P2080-581 | Activity P2080-581 | Not Started | 0 | 0 | 0 | 0 | 105 | 0 | 0 | Total Float > 20 | Activity ID: P2080-581<br>Activity Name: Activity P2080-581<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 105.0
P2080-582 | Activity P2080-582 | Not Started | 0 | 0 | 0 | 0 | 155 | 0 | 0 | Total Float > 20 | Activity ID: P2080-582<br>Activity Name: Activity P2080-582<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 155.0
P2080-583 | Activity P2080-583 | Not Started | 0 | 0 | 0 | 0 | 719 | 0 | 0 | Total Float > 20 | Activity ID: P2080-583<br>Activity Name: Activity P2080-583<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 719.0
P2080-586 | Activity P2080-586 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-586<br>Activity Name: Activity P2080-586<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-587 | Activity P2080-587 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-587<br>Activity Name: Activity P2080-587<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-588 | Activity P2080-588 | Not Started | 0 | 0 | 0 | 0 | 648 | 0 | 0 | Total Float > 20 | Activity ID: P2080-588<br>Activity Name: Activity P2080-588<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 648.0
P2080-590 | Activity P2080-590 | Not Started | 0 | 0 | 0 | 0 | 48 | 0 | 0 | Total Float > 20 | Activity ID: P2080-590<br>Activity Name: Activity P2080-590<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 48.0
P2080-591 | Activity P2080-591 | Not Started | 0 | 0 | 0 | 0 | 105 | 0 | 0 | Total Float > 20 | Activity ID: P2080-591<br>Activity Name: Activity P2080-591<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 105.0
P2080-592 | Activity P2080-592 | Not Started | 0 | 0 | 0 | 0 | 741 | 0 | 0 | Total Float > 20 | Activity ID: P2080-592<br>Activity Name: Activity P2080-592<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 741.0
P2080-593 | Activity P2080-593 | Not Started | 0 | 0 | 0 | 0 | 147 | 0 | 0 | Total Float > 20 | Activity ID: P2080-593<br>Activity Name: Activity P2080-593<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 147.0
P2080-596 | Activity P2080-596 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-596<br>Activity Name: Activity P2080-596<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-597 | Activity P2080-597 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-597<br>Activity Name: Activity P2080-597<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-598 | Activity P2080-598 | Not Started | 0 | 0 | 0 | 0 | 48 | 0 | 0 | Total Float > 20 | Activity ID: P2080-598<br>Activity Name: Activity P2080-598<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 48.0
P2080-599 | Activity P2080-599 | Not Started | 0 | 0 | 0 | 0 | 105 | 0 | 0 | Total Float > 20 | Activity ID: P2080-599<br>Activity Name: Activity P2080-599<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 105.0
P2080-600 | Activity P2080-600 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-600<br>Activity Name: Activity P2080-600<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-601 | Activity P2080-601 | Not Started | 0 | 0 | 0 | 0 | 105 | 0 | 0 | Total Float > 20 | Activity ID: P2080-601<br>Activity Name: Activity P2080-601<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 105.0
P2080-602 | Activity P2080-602 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-602<br>Activity Name: Activity P2080-602<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-603 | Activity P2080-603 | Not Started | 0 | 0 | 0 | 0 | 107 | 0 | 0 | Total Float > 20 | Activity ID: P2080-603<br>Activity Name: Activity P2080-603<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 107.0
P2080-604 | Activity P2080-604 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-604<br>Activity Name: Activity P2080-604<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-605 | Activity P2080-605 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-605<br>Activity Name: Activity P2080-605<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-606 | Activity P2080-606 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-606<br>Activity Name: Activity P2080-606<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-607 | Activity P2080-607 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-607<br>Activity Name: Activity P2080-607<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-608 | Activity P2080-608 | Not Started | 0 | 0 | 0 | 0 | 274 | 0 | 0 | Total Float > 20 | Activity ID: P2080-608<br>Activity Name: Activity P2080-608<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 274.0
P2080-610 | Activity P2080-610 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-610<br>Activity Name: Activity P2080-610<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-611 | Activity P2080-611 | Not Started | 0 | 0 | 0 | 0 | 105 | 0 | 0 | Total Float > 20 | Activity ID: P2080-611<br>Activity Name: Activity P2080-611<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 105.0
P2080-612 | Activity P2080-612 | Not Started | 0 | 0 | 0 | 0 | 737 | 0 | 0 | Total Float > 20 | Activity ID: P2080-612<br>Activity Name: Activity P2080-612<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 737.0
P2080-613 | Activity P2080-613 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-613<br>Activity Name: Activity P2080-613<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-617 | Activity P2080-617 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-617<br>Activity Name: Activity P2080-617<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-618 | Activity P2080-618 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-618<br>Activity Name: Activity P2080-618<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-619 | Activity P2080-619 | Not Started | 0 | 0 | 0 | 0 | 107 | 0 | 0 | Total Float > 20 | Activity ID: P2080-619<br>Activity Name: Activity P2080-619<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 107.0
P2080-620 | Activity P2080-620 | Not Started | 0 | 0 | 0 | 0 | 735 | 0 | 0 | Total Float > 20 | Activity ID: P2080-620<br>Activity Name: Activity P2080-620<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 735.0
P2080-621 | Activity P2080-621 | Not Started | 0 | 0 | 0 | 0 | 123 | 0 | 0 | Total Float > 20 | Activity ID: P2080-621<br>Activity Name: Activity P2080-621<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 123.0
P2080-622 | Activity P2080-622 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-622<br>Activity Name: Activity P2080-622<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-623 | Activity P2080-623 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-623<br>Activity Name: Activity P2080-623<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-627 | Activity P2080-627 | Not Started | 0 | 0 | 0 | 0 | 89 | 0 | 0 | Total Float > 20 | Activity ID: P2080-627<br>Activity Name: Activity P2080-627<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 89.0
P2080-631 | Activity P2080-631 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-631<br>Activity Name: Activity P2080-631<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-632 | Activity P2080-632 | Not Started | 0 | 0 | 0 | 0 | 102 | 0 | 0 | Total Float > 20 | Activity ID: P2080-632<br>Activity Name: Activity P2080-632<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 102.0
P2080-633 | Activity P2080-633 | Not Started | 0 | 0 | 0 | 0 | 634 | 0 | 0 | Total Float > 20 | Activity ID: P2080-633<br>Activity Name: Activity P2080-633<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 634.0
P2080-635 | Activity P2080-635 | Not Started | 0 | 0 | 0 | 0 | 27 | 0 | 0 | Total Float > 20 | Activity ID: P2080-635<br>Activity Name: Activity P2080-635<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 27.0
P2080-636 | Activity P2080-636 | Not Started | 0 | 0 | 0 | 0 | 633 | 0 | 0 | Total Float > 20 | Activity ID: P2080-636<br>Activity Name: Activity P2080-636<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 633.0
P2080-640 | Activity P2080-640 | Not Started | 0 | 0 | 0 | 0 | 99 | 0 | 0 | Total Float > 20 | Activity ID: P2080-640<br>Activity Name: Activity P2080-640<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 99.0
P2080-641 | Activity P2080-641 | Not Started | 0 | 0 | 0 | 0 | 728 | 0 | 0 | Total Float > 20 | Activity ID: P2080-641<br>Activity Name: Activity P2080-641<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 728.0
P2080-642 | Activity P2080-642 | Not Started | 0 | 0 | 0 | 0 | 25 | 0 | 0 | Total Float > 20 | Activity ID: P2080-642<br>Activity Name: Activity P2080-642<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 25.0
P2080-644 | Activity P2080-644 | Not Started | 0 | 0 | 0 | 0 | 726 | 0 | 0 | Total Float > 20 | Activity ID: P2080-644<br>Activity Name: Activity P2080-644<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 726.0
P2080-645 | Activity P2080-645 | Not Started | 0 | 0 | 0 | 0 | 630 | 0 | 0 | Total Float > 20 | Activity ID: P2080-645<br>Activity Name: Activity P2080-645<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 630.0
P2080-646 | Activity P2080-646 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-646<br>Activity Name: Activity P2080-646<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-649 | Activity P2080-649 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-649<br>Activity Name: Activity P2080-649<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-650 | Activity P2080-650 | Not Started | 0 | 0 | 0 | 0 | 39 | 0 | 0 | Total Float > 20 | Activity ID: P2080-650<br>Activity Name: Activity P2080-650<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 39.0
P2080-652 | Activity P2080-652 | Not Started | 0 | 0 | 0 | 0 | 749 | 0 | 0 | Total Float > 20 | Activity ID: P2080-652<br>Activity Name: Activity P2080-652<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 749.0
P2080-653 | Activity P2080-653 | Not Started | 0 | 0 | 0 | 0 | 865 | 0 | 0 | Total Float > 20 | Activity ID: P2080-653<br>Activity Name: Activity P2080-653<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 865.0
P2080-656 | Activity P2080-656 | Not Started | 0 | 0 | 0 | 0 | 39 | 0 | 0 | Total Float > 20 | Activity ID: P2080-656<br>Activity Name: Activity P2080-656<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 39.0
P2080-657 | Activity P2080-657 | Not Started | 0 | 0 | 0 | 0 | 35 | 0 | 0 | Total Float > 20 | Activity ID: P2080-657<br>Activity Name: Activity P2080-657<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 35.0
P2080-658 | Activity P2080-658 | Not Started | 0 | 0 | 0 | 0 | 93 | 0 | 0 | Total Float > 20 | Activity ID: P2080-658<br>Activity Name: Activity P2080-658<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 93.0
P2080-659 | Activity P2080-659 | Not Started | 0 | 0 | 0 | 0 | 99 | 0 | 0 | Total Float > 20 | Activity ID: P2080-659<br>Activity Name: Activity P2080-659<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 99.0
P2080-660 | Activity P2080-660 | Not Started | 0 | 0 | 0 | 0 | 200 | 0 | 0 | Total Float > 20 | Activity ID: P2080-660<br>Activity Name: Activity P2080-660<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 200.0
P2080-661 | Activity P2080-661 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-661<br>Activity Name: Activity P2080-661<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-662 | Activity P2080-662 | Not Started | 0 | 0 | 0 | 0 | 93 | 0 | 0 | Total Float > 20 | Activity ID: P2080-662<br>Activity Name: Activity P2080-662<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 93.0
P2080-663 | Activity P2080-663 | Not Started | 0 | 0 | 0 | 0 | 93 | 0 | 0 | Total Float > 20 | Activity ID: P2080-663<br>Activity Name: Activity P2080-663<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 93.0
P2080-666 | Activity P2080-666 | Not Started | 0 | 0 | 0 | 0 | 93 | 0 | 0 | Total Float > 20 | Activity ID: P2080-666<br>Activity Name: Activity P2080-666<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 93.0
P2080-667 | Activity P2080-667 | Not Started | 0 | 0 | 0 | 0 | 93 | 0 | 0 | Total Float > 20 | Activity ID: P2080-667<br>Activity Name: Activity P2080-667<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 93.0
P2080-668 | Activity P2080-668 | Not Started | 0 | 0 | 0 | 0 | 39 | 0 | 0 | Total Float > 20 | Activity ID: P2080-668<br>Activity Name: Activity P2080-668<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 39.0
P2080-675 | Activity P2080-675 | Not Started | 0 | 0 | 0 | 0 | 96 | 0 | 0 | Total Float > 20 | Activity ID: P2080-675<br>Activity Name: Activity P2080-675<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 96.0
P2080-676 | Activity P2080-676 | Not Started | 0 | 0 | 0 | 0 | 99 | 0 | 0 | Total Float > 20 | Activity ID: P2080-676<br>Activity Name: Activity P2080-676<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 99.0
P2080-677 | Activity P2080-677 | Not Started | 0 | 0 | 0 | 0 | 619 | 0 | 0 | Total Float > 20 | Activity ID: P2080-677<br>Activity Name: Activity P2080-677<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 619.0
P2080-678 | Activity P2080-678 | Not Started | 0 | 0 | 0 | 0 | 715 | 0 | 0 | Total Float > 20 | Activity ID: P2080-678<br>Activity Name: Activity P2080-678<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 715.0
P2080-681 | Activity P2080-681 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-681<br>Activity Name: Activity P2080-681<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-684 | Activity P2080-684 | Not Started | 0 | 0 | 0 | 0 | 711 | 0 | 0 | Total Float > 20 | Activity ID: P2080-684<br>Activity Name: Activity P2080-684<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 711.0
P2080-688 | Activity P2080-688 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-688<br>Activity Name: Activity P2080-688<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-689 | Activity P2080-689 | Not Started | 0 | 0 | 0 | 0 | 26 | 0 | 0 | Total Float > 20 | Activity ID: P2080-689<br>Activity Name: Activity P2080-689<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 26.0
P2080-690 | Activity P2080-690 | Not Started | 0 | 0 | 0 | 0 | 26 | 0 | 0 | Total Float > 20 | Activity ID: P2080-690<br>Activity Name: Activity P2080-690<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 26.0
P2080-691 | Activity P2080-691 | Not Started | 0 | 0 | 0 | 0 | 200 | 0 | 0 | Total Float > 20 | Activity ID: P2080-691<br>Activity Name: Activity P2080-691<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 200.0
P2080-692 | Activity P2080-692 | Not Started | 0 | 0 | 0 | 0 | 48 | 0 | 0 | Total Float > 20 | Activity ID: P2080-692<br>Activity Name: Activity P2080-692<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 48.0
P2080-693 | Activity P2080-693 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-693<br>Activity Name: Activity P2080-693<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-694 | Activity P2080-694 | Not Started | 0 | 0 | 0 | 0 | 51 | 0 | 0 | Total Float > 20 | Activity ID: P2080-694<br>Activity Name: Activity P2080-694<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 51.0
P2080-695 | Activity P2080-695 | Not Started | 0 | 0 | 0 | 0 | 48 | 0 | 0 | Total Float > 20 | Activity ID: P2080-695<br>Activity Name: Activity P2080-695<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 48.0
P2080-698 | Activity P2080-698 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-698<br>Activity Name: Activity P2080-698<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-699 | Activity P2080-699 | Not Started | 0 | 0 | 0 | 0 | 51 | 0 | 0 | Total Float > 20 | Activity ID: P2080-699<br>Activity Name: Activity P2080-699<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 51.0
P2080-700 | Activity P2080-700 | Not Started | 0 | 0 | 0 | 0 | 610 | 0 | 0 | Total Float > 20 | Activity ID: P2080-700<br>Activity Name: Activity P2080-700<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 610.0
P2080-701 | Activity P2080-701 | Not Started | 0 | 0 | 0 | 0 | 706 | 0 | 0 | Total Float > 20 | Activity ID: P2080-701<br>Activity Name: Activity P2080-701<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 706.0
P2080-703 | Activity P2080-703 | Not Started | 0 | 0 | 0 | 0 | 69 | 0 | 0 | Total Float > 20 | Activity ID: P2080-703<br>Activity Name: Activity P2080-703<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 69.0
P2080-704 | Activity P2080-704 | Not Started | 0 | 0 | 0 | 0 | 73 | 0 | 0 | Total Float > 20 | Activity ID: P2080-704<br>Activity Name: Activity P2080-704<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 73.0
P2080-705 | Activity P2080-705 | Not Started | 0 | 0 | 0 | 0 | 48 | 0 | 0 | Total Float > 20 | Activity ID: P2080-705<br>Activity Name: Activity P2080-705<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 48.0
P2080-706 | Activity P2080-706 | Not Started | 0 | 0 | 0 | 0 | 705 | 0 | 0 | Total Float > 20 | Activity ID: P2080-706<br>Activity Name: Activity P2080-706<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 705.0
P2080-708 | Activity P2080-708 | Not Started | 0 | 0 | 0 | 0 | 66 | 0 | 0 | Total Float > 20 | Activity ID: P2080-708<br>Activity Name: Activity P2080-708<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 66.0
P2080-713 | Activity P2080-713 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-713<br>Activity Name: Activity P2080-713<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-714 | Activity P2080-714 | Not Started | 0 | 0 | 0 | 0 | 53 | 0 | 0 | Total Float > 20 | Activity ID: P2080-714<br>Activity Name: Activity P2080-714<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 53.0
P2080-717 | Activity P2080-717 | Not Started | 0 | 0 | 0 | 0 | 697 | 0 | 0 | Total Float > 20 | Activity ID: P2080-717<br>Activity Name: Activity P2080-717<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 697.0
P2080-721 | Activity P2080-721 | Not Started | 0 | 0 | 0 | 0 | 38 | 0 | 0 | Total Float > 20 | Activity ID: P2080-721<br>Activity Name: Activity P2080-721<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 38.0
P2080-722 | Activity P2080-722 | Not Started | 0 | 0 | 0 | 0 | 46 | 0 | 0 | Total Float > 20 | Activity ID: P2080-722<br>Activity Name: Activity P2080-722<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 46.0
P2080-723 | Activity P2080-723 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-723<br>Activity Name: Activity P2080-723<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-724 | Activity P2080-724 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-724<br>Activity Name: Activity P2080-724<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-727 | Activity P2080-727 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-727<br>Activity Name: Activity P2080-727<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-728 | Activity P2080-728 | Not Started | 0 | 0 | 0 | 0 | 53 | 0 | 0 | Total Float > 20 | Activity ID: P2080-728<br>Activity Name: Activity P2080-728<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 53.0
P2080-730 | Activity P2080-730 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-730<br>Activity Name: Activity P2080-730<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-731 | Activity P2080-731 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-731<br>Activity Name: Activity P2080-731<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-732 | Activity P2080-732 | Not Started | 0 | 0 | 0 | 0 | 38 | 0 | 0 | Total Float > 20 | Activity ID: P2080-732<br>Activity Name: Activity P2080-732<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 38.0
P2080-733 | Activity P2080-733 | Not Started | 0 | 0 | 0 | 0 | 693 | 0 | 0 | Total Float > 20 | Activity ID: P2080-733<br>Activity Name: Activity P2080-733<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 693.0
P2080-734 | Activity P2080-734 | Not Started | 0 | 0 | 0 | 0 | 54 | 0 | 0 | Total Float > 20 | Activity ID: P2080-734<br>Activity Name: Activity P2080-734<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 54.0
P2080-738 | Activity P2080-738 | Not Started | 0 | 0 | 0 | 0 | 46 | 0 | 0 | Total Float > 20 | Activity ID: P2080-738<br>Activity Name: Activity P2080-738<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 46.0
P2080-741 | Activity P2080-741 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-741<br>Activity Name: Activity P2080-741<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-742 | Activity P2080-742 | Not Started | 0 | 0 | 0 | 0 | 33 | 0 | 0 | Total Float > 20 | Activity ID: P2080-742<br>Activity Name: Activity P2080-742<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 33.0
P2080-743 | Activity P2080-743 | Not Started | 0 | 0 | 0 | 0 | 690 | 0 | 0 | Total Float > 20 | Activity ID: P2080-743<br>Activity Name: Activity P2080-743<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 690.0
P2080-744 | Activity P2080-744 | Not Started | 0 | 0 | 0 | 0 | 690 | 0 | 0 | Total Float > 20 | Activity ID: P2080-744<br>Activity Name: Activity P2080-744<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 690.0
P2080-745 | Activity P2080-745 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-745<br>Activity Name: Activity P2080-745<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-746 | Activity P2080-746 | Not Started | 0 | 0 | 0 | 0 | 45 | 0 | 0 | Total Float > 20 | Activity ID: P2080-746<br>Activity Name: Activity P2080-746<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 45.0
P2080-747 | Activity P2080-747 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-747<br>Activity Name: Activity P2080-747<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-748 | Activity P2080-748 | Not Started | 0 | 0 | 0 | 0 | 53 | 0 | 0 | Total Float > 20 | Activity ID: P2080-748<br>Activity Name: Activity P2080-748<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 53.0
P2080-750 | Activity P2080-750 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-750<br>Activity Name: Activity P2080-750<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-751 | Activity P2080-751 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-751<br>Activity Name: Activity P2080-751<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-752 | Activity P2080-752 | Not Started | 0 | 0 | 0 | 0 | 687 | 0 | 0 | Total Float > 20 | Activity ID: P2080-752<br>Activity Name: Activity P2080-752<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 687.0
P2080-755 | Activity P2080-755 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-755<br>Activity Name: Activity P2080-755<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-757 | Activity P2080-757 | Not Started | 0 | 0 | 0 | 0 | 46 | 0 | 0 | Total Float > 20 | Activity ID: P2080-757<br>Activity Name: Activity P2080-757<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 46.0
P2080-762 | Activity P2080-762 | Not Started | 0 | 0 | 0 | 0 | 39 | 0 | 0 | Total Float > 20 | Activity ID: P2080-762<br>Activity Name: Activity P2080-762<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 39.0
P2080-764 | Activity P2080-764 | Not Started | 0 | 0 | 0 | 0 | 22 | 0 | 0 | Total Float > 20 | Activity ID: P2080-764<br>Activity Name: Activity P2080-764<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 22.0
P2080-765 | Activity P2080-765 | Not Started | 0 | 0 | 0 | 0 | 589 | 0 | 0 | Total Float > 20 | Activity ID: P2080-765<br>Activity Name: Activity P2080-765<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 589.0
P2080-773 | Activity P2080-773 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-773<br>Activity Name: Activity P2080-773<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-774 | Activity P2080-774 | Not Started | 0 | 0 | 0 | 0 | 31 | 0 | 0 | Total Float > 20 | Activity ID: P2080-774<br>Activity Name: Activity P2080-774<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 31.0
P2080-775 | Activity P2080-775 | Not Started | 0 | 0 | 0 | 0 | 681 | 0 | 0 | Total Float > 20 | Activity ID: P2080-775<br>Activity Name: Activity P2080-775<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 681.0
P2080-777 | Activity P2080-777 | Not Started | 0 | 0 | 0 | 0 | 39 | 0 | 0 | Total Float > 20 | Activity ID: P2080-777<br>Activity Name: Activity P2080-777<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 39.0
P2080-780 | Activity P2080-780 | Not Started | 0 | 0 | 0 | 0 | 583 | 0 | 0 | Total Float > 20 | Activity ID: P2080-780<br>Activity Name: Activity P2080-780<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 583.0
P2080-782 | Activity P2080-782 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-782<br>Activity Name: Activity P2080-782<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-783 | Activity P2080-783 | Not Started | 0 | 0 | 0 | 0 | 581 | 0 | 0 | Total Float > 20 | Activity ID: P2080-783<br>Activity Name: Activity P2080-783<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 581.0
P2080-784 | Activity P2080-784 | Not Started | 0 | 0 | 0 | 0 | 581 | 0 | 0 | Total Float > 20 | Activity ID: P2080-784<br>Activity Name: Activity P2080-784<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 581.0
P2080-788 | Activity P2080-788 | Not Started | 0 | 0 | 0 | 0 | 28 | 0 | 0 | Total Float > 20 | Activity ID: P2080-788<br>Activity Name: Activity P2080-788<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 28.0
P2080-789 | Activity P2080-789 | Not Started | 0 | 0 | 0 | 0 | 42 | 0 | 0 | Total Float > 20 | Activity ID: P2080-789<br>Activity Name: Activity P2080-789<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 42.0
P2080-790 | Activity P2080-790 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-790<br>Activity Name: Activity P2080-790<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-791 | Activity P2080-791 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-791<br>Activity Name: Activity P2080-791<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-792 | Activity P2080-792 | Not Started | 0 | 0 | 0 | 0 | 31 | 0 | 0 | Total Float > 20 | Activity ID: P2080-792<br>Activity Name: Activity P2080-792<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 31.0
P2080-795 | Activity P2080-795 | Not Started | 0 | 0 | 0 | 0 | 39 | 0 | 0 | Total Float > 20 | Activity ID: P2080-795<br>Activity Name: Activity P2080-795<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 39.0
P2080-796 | Activity P2080-796 | Not Started | 0 | 0 | 0 | 0 | 49 | 0 | 0 | Total Float > 20 | Activity ID: P2080-796<br>Activity Name: Activity P2080-796<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 49.0
P2080-797 | Activity P2080-797 | Not Started | 0 | 0 | 0 | 0 | 30 | 0 | 0 | Total Float > 20 | Activity ID: P2080-797<br>Activity Name: Activity P2080-797<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 30.0
P2080-801 | Activity P2080-801 | Not Started | 0 | 0 | 0 | 0 | 31 | 0 | 0 | Total Float > 20 | Activity ID: P2080-801<br>Activity Name: Activity P2080-801<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 31.0
P2080-803 | Activity P2080-803 | Not Started | 0 | 0 | 0 | 0 | 52 | 0 | 0 | Total Float > 20 | Activity ID: P2080-803<br>Activity Name: Activity P2080-803<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 52.0
P2080-804 | Activity P2080-804 | Not Started | 0 | 0 | 0 | 0 | 576 | 0 | 0 | Total Float > 20 | Activity ID: P2080-804<br>Activity Name: Activity P2080-804<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 576.0
P2080-809 | Activity P2080-809 | Not Started | 0 | 0 | 0 | 0 | 572 | 0 | 0 | Total Float > 20 | Activity ID: P2080-809<br>Activity Name: Activity P2080-809<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 572.0
P2080-823 | Activity P2080-823 | Not Started | 0 | 0 | 0 | 0 | 558 | 0 | 0 | Total Float > 20 | Activity ID: P2080-823<br>Activity Name: Activity P2080-823<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 558.0
P2080-824 | Activity P2080-824 | Not Started | 0 | 0 | 0 | 0 | 558 | 0 | 0 | Total Float > 20 | Activity ID: P2080-824<br>Activity Name: Activity P2080-824<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 558.0
P2080-831 | Activity P2080-831 | Not Started | 0 | 0 | 0 | 0 | 558 | 0 | 0 | Total Float > 20 | Activity ID: P2080-831<br>Activity Name: Activity P2080-831<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 558.0
P2080-832 | Activity P2080-832 | Not Started | 0 | 0 | 0 | 0 | 558 | 0 | 0 | Total Float > 20 | Activity ID: P2080-832<br>Activity Name: Activity P2080-832<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 558.0
P2080-833 | Activity P2080-833 | Not Started | 0 | 0 | 0 | 0 | 558 | 0 | 0 | Total Float > 20 | Activity ID: P2080-833<br>Activity Name: Activity P2080-833<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 558.0
P2080-834 | Activity P2080-834 | Not Started | 0 | 0 | 0 | 0 | 558 | 0 | 0 | Total Float > 20 | Activity ID: P2080-834<br>Activity Name: Activity P2080-834<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 558.0
P2080-844 | Activity P2080-844 | Not Started | 0 | 0 | 0 | 0 | 28 | 0 | 0 | Total Float > 20 | Activity ID: P2080-844<br>Activity Name: Activity P2080-844<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 28.0
P2080-877 | Activity P2080-877 | Not Started | 0 | 0 | 0 | 0 | 642 | 0 | 0 | Total Float > 20 | Activity ID: P2080-877<br>Activity Name: Activity P2080-877<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 642.0
P2080-878 | Activity P2080-878 | Not Started | 0 | 0 | 0 | 0 | 535 | 0 | 0 | Total Float > 20 | Activity ID: P2080-878<br>Activity Name: Activity P2080-878<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 535.0
P2080-884 | Activity P2080-884 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-884<br>Activity Name: Activity P2080-884<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-886 | Activity P2080-886 | Not Started | 0 | 0 | 0 | 0 | 111 | 0 | 0 | Total Float > 20 | Activity ID: P2080-886<br>Activity Name: Activity P2080-886<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 111.0
P2080-888 | Activity P2080-888 | Not Started | 0 | 0 | 0 | 0 | 526 | 0 | 0 | Total Float > 20 | Activity ID: P2080-888<br>Activity Name: Activity P2080-888<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 526.0
P2080-890 | Activity P2080-890 | Not Started | 0 | 0 | 0 | 0 | 80 | 0 | 0 | Total Float > 20 | Activity ID: P2080-890<br>Activity Name: Activity P2080-890<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 80.0
P2080-891 | Activity P2080-891 | Not Started | 0 | 0 | 0 | 0 | 86 | 0 | 0 | Total Float > 20 | Activity ID: P2080-891<br>Activity Name: Activity P2080-891<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 86.0
P2080-892 | Activity P2080-892 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-892<br>Activity Name: Activity P2080-892<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-893 | Activity P2080-893 | Not Started | 0 | 0 | 0 | 0 | 110 | 0 | 0 | Total Float > 20 | Activity ID: P2080-893<br>Activity Name: Activity P2080-893<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 110.0
P2080-894 | Activity P2080-894 | Not Started | 0 | 0 | 0 | 0 | 80 | 0 | 0 | Total Float > 20 | Activity ID: P2080-894<br>Activity Name: Activity P2080-894<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 80.0
P2080-895 | Activity P2080-895 | Not Started | 0 | 0 | 0 | 0 | 86 | 0 | 0 | Total Float > 20 | Activity ID: P2080-895<br>Activity Name: Activity P2080-895<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 86.0
P2080-896 | Activity P2080-896 | Not Started | 0 | 0 | 0 | 0 | 100 | 0 | 0 | Total Float > 20 | Activity ID: P2080-896<br>Activity Name: Activity P2080-896<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 100.0
P2080-897 | Activity P2080-897 | Not Started | 0 | 0 | 0 | 0 | 120 | 0 | 0 | Total Float > 20 | Activity ID: P2080-897<br>Activity Name: Activity P2080-897<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 120.0
P2080-898 | Activity P2080-898 | Not Started | 0 | 0 | 0 | 0 | 86 | 0 | 0 | Total Float > 20 | Activity ID: P2080-898<br>Activity Name: Activity P2080-898<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 86.0
P2080-901 | Activity P2080-901 | Not Started | 0 | 0 | 0 | 0 | 113 | 0 | 0 | Total Float > 20 | Activity ID: P2080-901<br>Activity Name: Activity P2080-901<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 113.0
P2080-904 | Activity P2080-904 | Not Started | 0 | 0 | 0 | 0 | 508 | 0 | 0 | Total Float > 20 | Activity ID: P2080-904<br>Activity Name: Activity P2080-904<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 508.0
P2080-905 | Activity P2080-905 | Not Started | 0 | 0 | 0 | 0 | 508 | 0 | 0 | Total Float > 20 | Activity ID: P2080-905<br>Activity Name: Activity P2080-905<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 508.0
P2080-906 | Activity P2080-906 | Not Started | 0 | 0 | 0 | 0 | 80 | 0 | 0 | Total Float > 20 | Activity ID: P2080-906<br>Activity Name: Activity P2080-906<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 80.0
P2080-909 | Activity P2080-909 | Not Started | 0 | 0 | 0 | 0 | 425 | 0 | 0 | Total Float > 20 | Activity ID: P2080-909<br>Activity Name: Activity P2080-909<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 425.0
P2080-911 | Activity P2080-911 | Not Started | 0 | 0 | 0 | 0 | 424 | 0 | 0 | Total Float > 20 | Activity ID: P2080-911<br>Activity Name: Activity P2080-911<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 424.0
P2080-914 | Activity P2080-914 | Not Started | 0 | 0 | 0 | 0 | 424 | 0 | 0 | Total Float > 20 | Activity ID: P2080-914<br>Activity Name: Activity P2080-914<br>Activity Status: Not Started<br><br>Variance - BL Project Duration: 0<br>Variance - BL Project Finish Date: 0<br>Total Float: 424.0